## Remittance
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Planning |  | Working list / WBS write | 업무 리스트 및 WBS 작성
|  | Function list / Policy definition | 기능 및 정책 정의서 작성
|  | Schedule output meeting | 일정 산출 회의
|  | Schedule output | 일정 산출
|  | Story board write | 화면정의서(스토리보드) 작성
Development (Issue) |  | Issue
| 1 | Country wise service ordering | 수신방법을 은행,현금,모바일 순으로 정렬 | 2days
| 1 | Registered from old app and did txn successfully. But It shows "KYC Update" while trying send money from new app | 모바일앱에서 회원가입 로직 변경 | 2days
| 1 | First log in always error in new apps, it says that account already login from other device | New app에서 처음 로그인시에 다른 장비에서 로그인하고 있는 메시지를 출력 | 1days | mobile checking
| 2 | Country bank list local language | 파트너에서 제공하는 은행명은 다국어로 표현
| 2 | Automatic system checking scheduler for web app, mobile app | 웹앱과 모바일앱에서 자동체킹 스케쥴러 | 2days
| 2 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈
Development (Core API) |  | Core API Development
| 1 | K-Bank API | K-Bank API | 2019-06-03 | 2019-06-21 |  | Ryan/Pralhad | bar: June 3 to June 5; June 7; June 10 to June 14; June 17 to June 21
Development (Core Module) |  | Core Module for Remittance System
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14 | bar: June 10 to June 14
| 2 | [Agrani-Bank] add module | Agrani-Bank 모듈 추가 | 2019-06-17 | 2019-06-21 | bar: June 17 to June 21
| 3 | Detail Message for failed transactions | 실패한 송금 메시지의 상세화
| 1 | Inbound Remittance Module | Inbound Remittance Module | 2019-06-07 | 2019-06-21 |  | Saroj/Max | bar: June 7; June 10 to June 14; June 17 to June 21
| 2 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | Ryan/Max
|  | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max
|  | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | Saroj/Pralhad
Development (Online) |  | Development in Online
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14 | bar: June 10 to June 14
|  | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28 |  | Max
| 1 | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈 | 2019-07-22 | 2019-08-02 |  | Max
| 2 | [KFTC] Customer Balance check Module | [KFTC] 잔액조회 API 모듈 | 2019-07-22 | 2019-08-02 |  | Max
| 3 | [KFTC] Domestic bank transfer using | [KFTC] 국내은행간 송금모듈 | 2019-08-19 | 2019-08-23 |  | Max
| 2 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | Ryan/Max
|  | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max
Development (Mobile API) |  | Development in Mobile app (API)
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14
|  | Customer Registration scenario change-login after KYC | 회원가입 시나리오 변경(KYC이후에 로그인 가능) | 시나리오필요
|  | ShinHan-Bank, IBK customer - KFTC Account Registration | 신한은행, IBK고객중에 여권고객에 대한 KFTC로 계좌등록
|  | [Agrani-Bank] add module | Agrani-Bank 모듈 추가 | 2019-06-17 | 2019-06-21
| 2 | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28
| 3 | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈 | 2019-07-22 | 2019-08-02
| 3 | [KFTC] Balance check Module | [KFTC] 잔액조회 API 모듈 | 2019-07-22 | 2019-08-02
| 2 | Domestic bank transfer using | 국내은행간 송금모듈 | 2019-08-19 | 2019-08-23
| 4 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | Ryan/Max
| 2 | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max
|  | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | Saroj/Pralhad
Development (Mobile App) |  | Development in Mobile app (iOS/Android)
|  | English keyboard is only accepted in Receivers detail | 수신자 정보에 영어만 사용가능 |  |  |  | James/Preyea
|  | Customer Registration scenario change-login after KYC | 회원가입 시나리오 변경(KYC이후에 로그인 가능) |  |  |  | James/Preyea
|  | ShinHan-Bank, IBK customer - KFTC Account Registration | 신한은행, IBK고객중에 여권고객에 대한 KFTC로 계좌등록 |  |  |  | James/Preyea
|  | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28 |  | James/Preyea
|  | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈 | 2019-07-22 | 2019-08-02 |  | James/Preyea
|  | [KFTC] Balance check Module | [KFTC] 잔액조회 API 모듈 | 2019-07-22 | 2019-08-02 |  | James/Preyea
|  | Domestic bank transfer using | 국내은행간 송금모듈 | 2019-08-19 | 2019-08-23 |  | James/Preyea
|  | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | James/Preyea
|  | UI change - Receiver setup field | 국가별 수신자 정보 UI변경 | 2019-06-24 | 2019-07-02 |  | James/Preyea
|  | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | James/Preyea
|  | On-App Chat | CS 메신저 기능 |  |  |  | James/Preyea
Test |  | Test
Publish

## Issue
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Engineer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Issue) |  | Issue
| 1 | Country wise service ordering | 수신방법을 은행,현금,모바일 순으로 정렬 |  |  | Completed
| 1 | Registered from old app and did txn successfully. But It shows "KYC Update" while trying send money from new app | customerMaster 테이블에 email이 있으면, customerMasterTemp 테이블 삭제 |  |  |  | Pralhad/Max
| 1 | [Nepal] First log in always error in new apps, it says that account already login from other device | New app에서 처음 로그인시에 다른 장비에서 로그인하고 있는 메시지를 출력 |  |  |  | Pralhad/Max
| 2 | Country bank list local language | 파트너에서 제공하는 은행명은 다국어로 표현 |  |  |  | Pralhad/Max
| new project | Automatic system checking scheduler for web app, mobile app | 웹앱과 모바일앱에서 자동체킹 스케쥴러 |  |  |  | Pralhad/Max
| 1 | [Nepal] Error message pop-up while login in Gme old app (20) | May be Encryption Key is different in html page and session value |  |  |  | Pralhad/Max
| 1 | [Indonesia] "Unauthorized Transaction" in every last step of txn in new app (3) | because of exchange rate value is different in exRateCalcHistory and @exrate declare @exrate float = 0.09332434800001 select 0.093324348 |  |  |  | Pralhad/Max
| 1 | [Indonesia] Receiver name already correct but still appear correction of the name to go to the secpnd step of sending money (1) | Same receiver Name entered in system and from API also throw invalid account error(Name compare with removing space,to lower case) |  |  |  | Pralhad/Max
| 1 | [Indonesia] Autodebit in new app, if we did mistake in information we can not correct it and do. We need to go back and do again from beginning (account verification) | Information change possible |  |  |  | Pralhad/Max
| 1 | [Myanmar] Middle name problem in old app | need to ask with Khin Yu |  |  |  | Pralhad/Max
| 1 | [Myanmar] Refund from wallet but not deposited to primary account (3 cases) | sometimes happen, usually its working (Sending request through KJ Bank API problem) request inserted in KJ_AUTO_REFUND but no api request found |  |  |  | Pralhad/Max
| 1 | [Mongolia] Please block the Mongolian keyboard in the receiver's details (10) | Development already done in new app,implement with reward point |  |  | Completed | Pralhad/Max

## Core API
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Core API) |  | Core API Development
| 1 | K-Bank API | K-Bank API | 2019-06-03 | 2019-06-21 |  | Ryan/Pralhad | bar: June 3 to June 5; June 7; June 10 to June 14; June 17 to June 21

## Core Module
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Core Module) |  | Core Module for Remittance System
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14 |  | Pralhad/Max | bar: June 10 to June 14
| 2 | [Agrani-Bank] add module | Agrani-Bank 모듈 추가 | 2019-06-17 | 2019-06-21 |  | Pralhad/Max | bar: June 17 to June 21
| 4 | Detail Message for failed transactions | 실패한 송금 메시지의 상세화
| 1 | Inbound Remittance Module | Inbound Remittance Module | 2019-06-07 | 2019-06-21 |  | Saroj/Max | bar: June 7; June 10 to June 14; June 17 to June 21
| 2 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | Ryan/Max
| 3 | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max | bar: June 24 to June 28; July 1 to July 2
| 3 | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | Saroj/Pralhad | bar: June 24 to June 28

## Online
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Online) |  | Development in Online
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14 | bar: June 10 to June 14
| 2 | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28 |  | Max | bar: June 17 to June 21; June 24 to June 28
| 1 | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈
| 2 | [KFTC] Customer Balance check Module | [KFTC] 잔액조회 API 모듈
| 3 | [KFTC] Domestic bank transfer using | [KFTC] 국내은행간 송금모듈
| 2 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 | 2019-07-03 |  |  | Ryan/Max
| 3 | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max | bar: June 24 to June 28; July 1 to July 2

## Mobile API
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Mobile API) |  | Development in Mobile app (API)
| 1 | Resend function errror even we changed partners for all corridors(Cambodia) | 파트너 체인지시 재송금 가능(캄보디아) | 2019-06-10 | 2019-06-14
|  | Customer Registration scenario change-login after KYC | 회원가입 시나리오 변경(KYC이후에 로그인 가능) | 시나리오필요
|  | ShinHan-Bank, IBK customer - KFTC Account Registration | 신한은행, IBK고객중에 여권고객에 대한 KFTC로 계좌등록
|  | [Agrani-Bank] add module | Agrani-Bank 모듈 추가 | 2019-06-17 | 2019-06-21
| 2 | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28
| 3 | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈
| 3 | [KFTC] Balance check Module | [KFTC] 잔액조회 API 모듈
| 2 | Domestic bank transfer using | 국내은행간 송금모듈
| 4 | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | Ryan/Max
| 2 | UI change - Receiver setup field | 국가별 수신자 정보리스트 | 2019-06-24 | 2019-07-02 |  | Ryan/Max
|  | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | Saroj/Pralhad

## Mobile App
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [7 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity |  | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Development (Mobile App) |  | Development in Mobile app (iOS/Android)
|  | English keyboard is only accepted in Receivers detail | 수신자 정보에 영어만 사용가능 |  |  |  | James/Preyea
|  | Customer Registration scenario change-login after KYC | 회원가입 시나리오 변경(KYC이후에 로그인 가능) |  |  |  | James/Preyea
|  | ShinHan-Bank, IBK customer - KFTC Account Registration | 신한은행, IBK고객중에 여권고객에 대한 KFTC로 계좌등록 |  |  |  | James/Preyea
|  | [KFTC] Token refresh logic (1-year) | [KFTC] 토큰 갱신 모듈(1년) | 2019-06-17 | 2019-06-28 |  | James/Preyea
|  | [KFTC] Auto Refund Module | [KFTC] 입금이체 API 모듈 |  |  |  | James/Preyea
|  | [KFTC] Balance check Module | [KFTC] 잔액조회 API 모듈 |  |  |  | James/Preyea
|  | Domestic bank transfer using | 국내은행간 송금모듈 |  |  |  | James/Preyea
|  | [KJ-Bank] multiple virtual account Module | [광주은행] 복수개의 가상계좌 모듈 |  |  |  | James/Preyea
|  | UI change - Receiver setup field | 국가별 수신자 정보 UI변경 | 2019-06-24 | 2019-07-02 |  | James/Preyea
|  | Mobile-App Popup Notice | 팝업공지 | 2019-06-24 | 2019-06-28 |  | James/Preyea
|  | On-App Chat | CS 메신저 기능 |  |  |  | James/Preyea

## Test-Publish
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad |  | Plan Color
Completion Color
Work Breakdown Structure | [6 empty] | June | [29 empty] | July | [30 empty] | Remarks
Phase | Priority | Activity | Start Date | End Date | Completed | Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Test |  | Test
Publish