## Sheet1
PM : Max,Pralhad
Phase | Priority | Activity |  | Duration | Architent(Design) - Architecture design - DB design - Function list design - Story board(Scenario) | Core | Online | API | iOS,Android | Test(Publish) | Total | Incentive
Project |  | Project Contents
| 1 | Thunes for Myanmar |  | 7. 4 ~ 7. 11
| 2 | Lyhour API for Cambodia bank deposit |  | 7. 8 ~ 7. 30
| 3 | Inbound (Online, API, App) 2nd phase | Inbond 프로젝트 2번째 페이지 | 7. 12 ~ 7. 30
| 4 | Shinhan and IBK bank about accounts created with passport. | 신한은행,IBK 은행은 KFTC만을 이용한 송금 | 7. 22 ~ 8. 8
| 5 | Agrani bank/Islami Bank not added to new app |  | 8. 13 ~ 8. 20
| 6 | KJ (Auto-remit for multiple-accounts use) | KJ(복수가상계좌를 이용한 자동송금)
| 1 | Mobile app - Registration logic - Calcurator in first screen - Dynamic receiver setup - Send Txn process same as web - Resend method not to check anything | 온라인과 앱에서의 회원가입방식이 달라서 발생하는 문제에 대한 회원가입변경 | 7. 8 ~ 7. 29
| 2 | Chatting app in app |  | 7. 5 ~ 7. 19
| 3 | Mobile app popup notice
| 4 | Reward/Coupon System 2nd phase | 포인트/쿠폰 2번째 페이지
| 5 | KFTC(Auto-refund, balance, Domestic-bank transfer) | KFTC(입금이체,잔액조회,로컬은행간 거래)
| 6 | Saving bank virtual account | 저축은행 가상계좌 도입