## Sheet1
|  | 분석 | 설계 | 구현 | 테스트 | 배포
2019-07-05 | 금 | Thuns for Myanmar | Thuns for Myanmar
2019-07-06 | 토
2019-07-07 | 일
2019-07-08 | 월 | Lyhour API Registration logic (app)
2019-07-09 | 화 | Calculate in first screen | Lyhour API
2019-07-10 | 수 | Dynamic receiver setup | Lyhour API |  | Thuns for Myanmar
2019-07-11 | 목 | Send Txn process same as web | Lyhour API |  | Thuns for Myanmar
2019-07-12 | 금 | Inbound(Online, App) 2nd Phase Resend method not to check anything
2019-07-13 | 토
2019-07-14 | 일
2019-07-15 | 월 |  | Inbound(Online, App) 2nd Phase
2019-07-16 | 화 |  | Inbound(Online, App) 2nd Phase
2019-07-17 | 수 |  | Inbound(Online, App) 2nd Phase
2019-07-18 | 목 |  | Inbound(Online, App) 2nd Phase |  |  | Thuns for Myanmar
2019-07-19 | 금 |  | Inbound(Online, App) 2nd Phase
2019-07-20 | 토
2019-07-21 | 일
2019-07-22 | 월 | Shinhan,IBK-KFTC |  |  | Registration logic
2019-07-23 | 화 |  | Shinhan,IBK-KFTC |  | Inbound(Online, App) 2nd Phase Calculate in first screen
2019-07-24 | 수 |  | Shinhan,IBK-KFTC |  | Inbound(Online, App) 2nd Phase Dynamic receiver setup
2019-07-25 | 목 |  | Shinhan,IBK-KFTC |  | Inbound(Online, App) 2nd Phase Lyhour API Dynamic receiver setup
2019-07-26 | 금 |  | Shinhan,IBK-KFTC |  | Inbound(Online, App) 2nd Phase Lyhour API Send Txn process same as web
2019-07-27 | 토
2019-07-28 | 일
2019-07-29 | 월 |  |  |  | Inbound(Online, App) 2nd Phase Shinhan,IBK-KFTC Resend method not to check anything
2019-07-30 | 화 |  |  |  | Inbound(Online, App) 2nd Phase Shinhan,IBK-KFTC | Registration logic Calculate in first screen Dynamic receiver setup Send Txn process same as web Resend method not to check anything
2019-07-31 | 수 |  |  |  | Shinhan,IBK-KFTC | Lyhour API
2019-08-01 | 목 |  |  |  | Shinhan,IBK-KFTC | Lyhour API
2019-08-02 | 금
2019-08-03 | 토
2019-08-04 | 일
2019-08-05 | 월
2019-08-06 | 화 |  |  |  |  | Inbound(Online, App) 2nd Phase
2019-08-07 | 수 |  |  |  |  | Inbound(Online, App) 2nd Phase
2019-08-08 | 목 | Agrani bank/Islami bank add to new app |  |  |  | Shinhan,IBK-KFTC
2019-08-09 | 금 |  | Agrani bank/Islami bank
2019-08-10 | 토
2019-08-11 | 일
2019-08-12 | 월 |  | Agrani bank/Islami bank
2019-08-13 | 화 |  |  | Agrani bank/Islami bank
2019-08-14 | 수 |  |  | Agrani bank/Islami bank
2019-08-15 | 목 |  |  | Agrani bank/Islami bank
2019-08-16 | 금 |  |  | Agrani bank/Islami bank
2019-08-17 | 토
2019-08-18 | 일
2019-08-19 | 월 |  |  |  | Agrani bank/Islami bank
2019-08-20 | 화 |  |  |  | Agrani bank/Islami bank
2019-08-21 | 수 |  |  |  |  | Agrani bank/Islami bank
2019-08-22 | 목 | KJ-Auto remit for multiple-accounts use
2019-08-23 | 금 |  | KJ-Auto remit for multiple-accounts use
2019-08-24 | 토
2019-08-25 | 일
2019-08-26 | 월 |  | KJ-Auto remit for multiple-accounts use
2019-08-27 | 화 |  | KJ-Auto remit for multiple-accounts use
2019-08-28 | 수 |  | KJ-Auto remit for multiple-accounts use
2019-08-29 | 목 |  | KJ-Auto remit for multiple-accounts use
2019-08-30 | 금 |  | KJ-Auto remit for multiple-accounts use
2019-08-31 | 토