## 7월29일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-100 | Change to registration logic(Android) | 9h | Preyea | Channel IO integration from Splash Screen Second Flow added after registration i.e. - Registration -> KYC -> Penny Test - > Home Previous flow only consist of - Login -> KYC -> Penny Test -> Home Realtime validation added in - Registration Screen (User Id) - KYC Verification Id Type and Verification Id Number
| GMER-99 | Change to registration logic(iOS) |  | James | 1. change login process 2. add validate userid
| GMER-58 | Inbound 2nd Phase(Core) |  | Manoj | Work in scheduler for paid Transaction Testing for registration & penny test from schedular Testing for Paid Transaction
| GMER-126 | Exam Bank API |  | Ganesh | Study API document Design API frame work create controller , business , request , response , service , repository class , create digital signature class generate signature, has data , write function for encrypt and decrypt method configuration credentials keys has key etc.

## 7월30일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-100 | Change to registration logic(Android) | 9h | Preyea | 1. Development completed for new registration flow. 2. Now testing, -New Customer Registration -Real Name Validation -And overall server side integration and testing
| GMER-99 | Change to registration logic(iOS) |  | James | 1. add validate NationalId, passport, AlienCard 2. Test Flow 1. register -> kyc -> penneyTest -> Home 3. Test Flow 2. register -> kyc -> exit app -> login -> penneyTest -> Home
| GMER-58 | Inbound 2nd Phase(Core) |  | Manoj | Staging deployment and testing
| GMER-98 | Change to registration logic(API) | 8h | Saroj | 1. Debug and resolve the bugs mobile team identified during registration, KYC submits and realtime validation. 2. resolve the penny test testing bug to test the mobile app 3. Debug, Fix and Deploy the application in the server multiple time.
| GMER-126 | Exam Bank API |  | Ganesh | add flowing method in controller Ping ExRate accountValidation sendTransaction modifyTransaction create following model class RequestMessage,Header,Data,Security implement following method in business layer GetHeader,GetTheBalanceserviceData,sendtxnData,SendTransaction
| GMER-18 | Change to registration logic |  | Ram | Updated kyc registration end point Remove mobile number and native country while registering kyc Added email and date of birth while registering kyc. Prepared postman test cases for registration change and kyc change

## 7월31일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-100 | Change to registration logic(Android) | 9h | Preyea | Minor fixes which includes: -Reactive validation fixes for verification id number and user id in registration screen. -Wallet number appended in failed popup in every api response -Layout and view fixes in splash screen, and register screen Translation for new feature completely added for following countries: Note :- Myanmar marketing head just informed me that in some devices the myanmar translation is not working for android. So until troubleshooting and finding the issue, myanmar translation is not implemented in android.
| GMER-99 | Change to registration logic(iOS) |  | James
| GMER-58 | Inbound 2nd Phase(Core) | 9H | Manoj | Testing in the Staging server and fix the error some tested account no 01SR112233 01SR112234 01SR112235 24062050Pathak 01SR112236
| GMER-98 | Change to registration logic(API) | 8h | Saroj | Resolve the issue identified by the mobile team. Deployed the application multiple times to see the changes applied
| GMER-127 | Check Balance | 1D | Ganesh | create BLNHeaderfunction , BLNkData for for checking balance create function for signature and hash data create CheckBalance function
| GMER-18 | Change to registration logic |  | Ram
| GMER-109 | Shinhan, IBK Bank realname verification using KFTC(Core) | 6H | Saroj | Checked the Bypass the bank check during loading of the customer detail for approval. Enabled the Approve button for IBK and Shinhan with passport as idType Bypass the message "Account Name in Bank is required" for IBK and Shinhan b Updated the transaction in the Live to resolve the transaction issue. Analysis of the issues of the transaction for being failed.