## 8월1일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-99 | Change to registration logic(iOS) | 1d | James | 1. release 2.4.0 1) Changed first screen to exchange rate 2) Changed business logic of registration 3) Added Channel Talk at First screen, Home screen 4) Thunes for Myanmar
| GMER-111 | Shinhan, IBK Bank realname verification using KFTC(Online) | 1d | Saroj | Changed the stored procedure to check for the KFTC only customer. a Created method to call the stored procedure. Checking the customer detail and show popup after login Added the popup with the option to check to Add Auto debit and redirect to the auto debit page Reject the transaction that is failed Delete the no. of customer New customer registration helping
| GMER-109 | Shinhan, IBK Bank realname verification using KFTC(Core) | 9H | Saroj | Updated the transaction in the Live to resolve the transaction issue. Analysis of the issues of the transaction for being failed.
| GMER-58 | Inbound 2nd Phase(Core) | 3H | Manoj | Testing in staging server
| GMER-140 | On Behalf of Txn | 6h | Manoj | Testing on a staging server 1.Send Test TXN in Cambodia 2. Myanmar 3.Nepal 4.Mongolia Error fixing while testing
| GMER-100 | Change to registration logic(Android) | 1D | Preyea | Verification Id validation fixes for Driving license Id type. App published to play store and waiting for review
| GMER-141 | IT technical support | 1d | Ram | 1. Full account validation of Ibbl account deposit in GME Online 2. Supports for the following issues:- (1) futureman192@gmail.com please check why the transaction fail (2) phoeaung80@gmail.com transaction fail by old app. (3) Country sending limit is not defined or exceed (4) Input order placement to ria fails 3. The link for the support doc is (1) https://docs.google.com/spreadsheets/d/1NPfYKqxPs8VfYuBgaLkvhmiRu8_Yj8PInS8tdYItvdw/edit#gid=2100473590
| GMER-127 | Check Balance | 1d | Ganesh | create signature and has data send request to Eximbank side to verify signature communicate with Eximbank API group to verify signature but there some issue, Try to verify signature.

## 8월2일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-22 | Dynamic receiver setup(iOS) | 2h | James | 1. Discuss about ui logic & business logic with Preyea
| GMER-92 | Send Txn process same as web(iOS) | 2h | James | 1. Discuss about ui logic and business logic with Preyea
| GMER-111 | Shinhan, IBK Bank realname verification using KFTC(Online) | 1d | Saroj | Checked the popup in the online system. Resolve the issue of showing pop up even customer is KFTC already registered. Deploy the system in STAGING Day to Day support in Live system.
| GMER-5 | Inbound 2nd Phase | 4h | Manoj | Inbound test with Mr.max Share test case file in Jira
| GMER-140 | On Behalf of Txn | 6h | Manoj | Testing in staging and File prepare for live deployment
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea | 1) Brainstormed for the new send money txn flow in app. 2) Country Listing mockup design developed
| GMER-141 | IT technical support | 1d | Ram | (1)Issues solved for the issues:- - Invalid agentcode in xpress - logout issues in app - auto-debit registration issues - Inactive customer issue - Ibbl account validation testing
| GMER-139 | GME website enhancement and updates | 4h | Ganesh | change website according to ppt provides
| GMER-127 | Check Balance | 4h | Ganesh | communicate with exmibank group for verify signature change change request parameter according their suggestion and again send request

## 8월5일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-92 | Send Txn process same as web(iOS) | 1d | James | 1. new make select country view 2. refactor select recipients view 3. determined UI Logic of new send money process
| GMER-111 | Shinhan, IBK Bank realname verification using KFTC(Core) | 1d | Saroj | changes the issue tracked during testing. Deployed the system in Staging. General System Support Updated the transaction from mail Tracking the issue of the transactions that are failed.
| GMER-59 | Inbound 2nd Phase(Online) | 3h | Manoj | Add receiver bank module in online system published in staging server and testing
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea | Discuss with Core team for the new improvised flow including dynamic reciever setup within Send Money Process. Payout Country Selection screen revamped and made exactly like IOS suggested by James.
| GMER-127 | Check Balance | 1d | Ganesh | communicate with eximbank api group configuration api with new credentials send mail to verify signature

## 8월6일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-92 | Send Txn process same as web(iOS) | 1d | James | 1. discussed about ui logic 2. implement send money process based on ui logic
| GMER-126 | Exim Bank API | 8h | Saroj | Daily support and another general transaction update in production Guided the Nepal Team regarding signature generation, encryption, and hashing. Checked the method developed for generating the signature, encrypting data and hashing
| GMER-58 | Inbound 2nd Phase(Core) | 3h | Manoj | Testing Inbound TXN reports
| GMER-59 | Inbound 2nd Phase(Online) | 3h | Manoj | Hold Txn Process Txn Txn Details Paid Txn for inbound testing in staging server
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea | Final send money flow confirmed. Successfully added receiver listing and real time account validation added in existing send money flow.
| GMER-141 | IT technical support | 4h | Ram | 1) Issues Solved: kojoe457@gmail.com please check why transaction fail. first last name all correct, new customer Transaction failed in Cambodia Please why its fail zzulaatur@yahoo.com 2) Details of the issues solved are shown in excel sheet link... 3) https://docs.google.com/spreadsheets/d/1NPfYKqxPs8VfYuBgaLkvhmiRu8_Yj8PInS8tdYItvdw/edit#gid=1392289540
| GMER-127 | Check Balance | 1d | Ganesh | send email to eximbak to verify signature take feedback from eximbank and re try . finally found issue in MD5Hash function Try to fixed issue

## 8월7일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-92 | Send Txn process same as web(iOS) | 9h | James | 1. Select Country View Optimization - add last transaction history (top 5) - add customer native country - add send money available countries
| GMER-126 | Exim Bank API | 8h | Saroj | developed the signature hashing function and tested. Send email to Exim bank team regarding the issue faced. Re factor the signature and identified the issues. Changed the logic causing the same issues. Hash and signature successfully generated. Guided Nepal team to further develop the required methods, Identify the issue with the transaction in the live system
Manoj
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea | 1) Payout Country Selection and Recent Transaction View development done. Now waiting for api integration As per requirement given from the mail: https://ovenapp.io/view/k4oy3pLohdoPpDplww20qnJ4zROQ3WFC/X6Inu
| GMER-141 | IT technical support | 4h | Ram | IT support for the following issues Transaction hold issue for the controlNo 80918078696 through tranglo api Error sending transaction for the user anwer_awais@yahoo.com error when sending money to wallet ronedaustria@yahoo.com
| GMER-128 | Check Account EIB | 4h | Ganesh | send email to verify request and response crate function for verify account Add getstatic class for serialization and deserialization xml
| GMER-127 | Check Balance | 4h | Ganesh | implement SendTransaction method for balance check modifed SendTransaction method for verify signature finally verify signature and got responses from eximbank

## 8월8일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-92 | Send Txn process same as web(iOS) | 9h | James | 1. Change Send money process 1) Select Recipient - Add Recipient ( add Payment mode, recipient's account number etc ) 2) Select account 3) Set send money amount 4) Verification of transaction 5) Send money
| GMER-144 | Partner reponse log report | 2h | Manoj | Sample query make
Manoj
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea
Ram
| GMER-139 | GME Website enhancement and updates | 8h | Ganesh | update website according to ppt provide published in UAT
| GMER-127 | Check Balance | 4h | Ganesh | implement SendTransaction method for balance check modifed SendTransaction method for verify signature finally verify signature and got responses from eximbank

## 8월 9일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-22 | Dynamic Receiver Setup | 8h | James | 1. Refactored recipient list view for dynamic receiver reactive user interaction
| GMER-141 | IT technical support | 4h | Ram | 1. Support for the IT issues 1) aungsanlinn715@gmail.com please check why txn fail for malaysia 2) checking the status of 80121065651
| GMER-93 | Send Txn process same as web(Android) | 9h | Preyea | New flow and API discussion with Backend Team. UI and memory optimization in Splash Screen.

## 8월 12일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-145 | NI Bank Cancel-transaction from core system | 4h | Manoj | Development Done in Core system
| GMER-113 | Shinhan,IBK Bank realname verification using KFTC(Android) | 3h | Preyea | API Integration done. UI flow managing now to redirect to KFTC registration screen
| GMER-117 | Dynamic Receiver Setup(Android) | 6h | Preyea | Discussion with API team to confirm the data structure for dynamic validation of receiver setup
| GMER-112 | Shinhan,IBK Bank realname verification using KFTC(iOS) | 1d | James | 1. Define about how to show regist Auto debit view 2. make logic
| GMER-110 | Shinhan,IBK Bank realname verification using KFTC(API) | 8h | Saroj | Changes made in the Api Controller in JsonRx. Changes the "mobile_proc_userLogin" procedure Changes the "mobile_proc_customerMaster" Procedure Analyze the problematic transaction and identify the cause. updated the transaction of mongolia

## 8월 13일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-141 | IT Technical support | 4h | Ram | IT supports for the following issues: 1)Yanlinaung90@gmail.com plz check why previous txn failed. Already exceed the limitation 2)yanmyoaung5226@gmail.com plz check why the txn failed? Customer can't take the error screenshot due to security systems 3)cannot transfer money to wallet Khuramshahzadks723@gmail.com 4)zayyakyaw600@gmail.com please check the reason why the previous txn failed?
| GMER-132 | Transfers to EIB Account | 3h | Ganesh | Transfers to EIB Account send transaction to EIB account transaction send successfully got response from exmin bank
| GMER-128 | Check Account EIB | 3h | Ganesh | Check Account EIB send transaction to exmin bank and got response successfully
| GMER-115 | Dynamic Receiver Setup(API) | 4h | Manoj | API development In UAT project New api name: mobile/receiver/ {customer} /dynamicField
| GMER-113 | Shinhan,IBK Bank realname verification using KFTC(Android) | 9h | Preyea | API integration mocked and tested successfully. UI flow handled and dim effect added for auto debit redirect notification Wrote UNIT Test regarding all different type of notification possibility that our UI can handle.
| GMER-112 | Shinhan,IBK Bank realname verification using KFTC(iOS) | 5h | James | 1. implemented move regist auto debit view
| GMER-110 | Shinhan,IBK Bank realname verification using KFTC(API) | 8h | Saroj | Exception raised due to value not retrieved from database resolved. Tested the application locally. Deployed the system. General IT Support in Kakao. The general task from email.

## 8월 14일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-141 | IT Technical Issue | 4h | Ram | IT supported issues (1) Fetching the wing code (2) auto-debit failed (3)kyaw2winn82@gmail.com please check why txn failed
| GMER-139 | GME website enhancement and updates | 8h | Ganesh | update website according provide in ppt and email
| GMER-115 | Dynamic Receiver Setup(API) | 4h | Manoj | *New endpoint develop in Uat server * 1.http://gmeuat.gmeremit.com:5022/swagger/ui/index#!/Receiver/Receiver_DynamicReceiverField
| GMER-117 | Dynamic Receiver Setup(Android) | 9h | Preyea | Receiver list fetch api integration and ui development complete. Receiver Add/Edit Screen Form Reactive UI Validation Rule added. Need Discussion with Core Team regarding Add, Edit and Delete API endpoints, weather existing api can be reused or not.
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. apply api side

## 8월 16일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-141 | IT Technical Issue | 4h | Ram | IT support tasks: 1) 80544582191 is it also waiting state at partner side? 2) It seems Mongolian txns after 7pm all don’t paid. Is it anyway to check this?
| GMER-93 | Send Txn process same as web(Android) | 3h | Preyea | Refactoring Current Send Money Flow to adjust recipient parameters obtained from receiver listing screen.
| GMER-117 | Dynamic receiver setup(Android) | 6h | Preyea | Reciever listing screen revamped and search functionality added.
| GMER-116 | Dynamic receiver setup(iOS) | 1d | James | 1. fetch Recipients discuss response spec (add districtID, countryID etc) apply these API in iOS

## 8월 19일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | Unit test wrote for each dynamic validation rule. UI Fixes Added support for Keyboard type.
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. Discussed about Dynamic receiver field 2. Make UI dynamic receiver view
| GMER-25 | Send Txn process same as web | 8h | Saroj | -Changed the stored procedure for adding the receiver. -Changed the SP for modifying the receiver and deleting the receiver. -Added the method for adding and modifying the receiver in a controller class and other service classes.F2 -Analysis of the issues from the kakao to track down the bug. -Update the database as per required.
| GMER-143 | Live Support | 9h | Manoj | *On behalf of txn issue resolved in Live system * one test TXN send to Nepal and cancel *Mongolia Hold Transactions Resend, Cancel * *Kakao Issue resolved * *Cancel Transaction * 10883850 E198190819082951001 10883856 E198190819083641396 10883872 E198190819090012695 *Meeting with IT Team for Dynamic Receiver setup

## 8월 20일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. Design UI about Dynamic Receiver setup view 2. Implementation Dynamic Receiver setup view
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | Add Receiver and Edit Receiver Use Case Flow separated so that both can evolve independently without affecting each other.
| GMER-25 | Send Txn process same as web | 2h | Saroj | Analysis of the issues from the kakao to track down the bug. Update the database as per required.
| GMER-142 | Live System support | 4h | Manoj | Live Support Mongolia Txn Resend Penny Test
| GMER-115 | Dynamic Receiver setup(API) | 5h | Manoj | API Endpoint discuss - Get CountryList, ServiceType List SP Create
| GMER-141 | IT technical support | 8h | Ram | 1. IT support tasks: - 80544582191 is it also waiting state at partner side? - It seems Mongolian txns after 7pm all don’t paid. Is it anyway to check this? 2. IT supported issues - Fetching the wing code - auto-debit failed - kyaw2winn82@gmail.com please check why txn failed

## 8월21일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) |  | James | 1. Dynamic Receiver Setup UI Implement Flag at country, mobile field Dynamic setup by server-side's response
| GMER-117 | Dynamic Receiver Setup(Android) |  | Preyea | Dynamic view validation update fixes
Saroj
| GMER-143 | Live Support |  | Manoj

## 8월22일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) |  | James | 1. Add Currency 2. Implement keyboard type by KeyboardType value 3. Implement exist recipient move to edit view
| GMER-117 | Dynamic Receiver Setup(Android) |  | Preyea | Validation rule applied to all form view.
| GMER-25 | Send Txn process same as web |  | Saroj | All Daily support for issues in kakao and email. Transaction issue analysis for failed transaction Worked on the receiver setup and changed the API according to the requirement of the mobile team.
| GMER-143 | Live Support |  | Manoj | Update TXN details and Resend Mongolia Transactions manually Cancel Mongolia Transactions Update Swift code for Vietnam

## 8월23일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-92 | Send Txn process same as web(iOS) |  | James | 1. Change send money process remove payout mode view directly move exchange rate view
| GMER-117 | Dynamic Receiver Setup(Android) |  | Preyea | Api Integration started for Dynamic validation related API end points Validation fixes for existing fields
| GMER-93 | Send Txn process same as web(Android) |  | Preyea | Removed Payout Mode Selection View from Send Money Flow since reciever list already have selected payout mode
| GMER-25 | Send Txn process same as web |  | Saroj | Analyze the issues at kakao and help the cs team with the reason of being txn failed. Update the penny test voucher Modified the payload for add and modify the receiver. this includes lastname1, lastname2, locallastName1, locallastName2, and added fields like fullname, localfullName
| GMER-143 | Live Support |  | Manoj | Resend Mongolia Transactions manually Penny Test

## 8월 26일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. add validate account logic 2. when edit, set exist recipient data 3. when search branch, add api
| GMER-93 | Send Txn process same as web(Android) | 1h | Preyea | Payout Mode removed successfully from send money process. Testing is due.
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | UI flow and dynamic validation completed. However api integration not completed and testing is due.
| GMER-25 | Send Txn process same as web |  | Saroj | Changed the Stored procedure that retrieves the receiver list and added both id's and text for static data. (PROC_MOBILE_RECEIVER_INFORMATION) Changes made to adjust the changed made in SP ("GetReceiverInformation"). added the logic to exclude the real name check for customer registered via Shinan and IBK bank with Passport as Id Type.
| GMER-22 | Dynamic Receiver Setup | 3h | Manoj | API endpoints change Sp changes
| GMER-143 | Live Support | 3h | Manoj | Mongolia Resend TXn kakao Issue resolved Penny test

## 8월 27일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. Optimize UI 2. Optimize dynamic receiver fields
| GMER-93 | Send Txn process same as web(Android) | 3h | Preyea | Bug fixes while calculating exrate for payout Country Srilanka and Nigeria.
| GMER-117 | Dynamic receiver setup(Android) | 6h | Preyea | Local testing started for recipient add/modify/delete and dynamic validation. End-to-End testing with API is due and will be carried out once dynamic setup is completed on core system.
Saroj
| GMER-143 | Live Support | 9h | Manoj | Resend Mongolia TXNs Update WIngs duplicate code Live support Discuss with MAX for the invalid transaction amount issue

## 8월 28일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. Staging Test Myanmar 2. UI Optimization Select Recipients list UI Dynamic Recipient Setup UI
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | Dynamic validation fixes for branch. Branch Validation rule override mechanism added depending upon "IsBranchRequired" flag while editing recipient. Myanmar recipient add/edit/delete testing started.
Saroj
| GMER-143 | Live Support | 6h | Manoj
| GMER-126 | Exim Bank API |  | Ram | Added account validation method in Online GME Added account validation method in Exim Bank Api Created sp: PROC_PROCESS_TRAN_EXIM Updated sp: proc_online_sendPageLoadData Prepared Send transaction request for exim bank api Transaction tested through postman Added GateWay field in tblpartnerwise country
| GMER-153 | Dynamic Receiver Setup(Field Setup) | 5h | Ganesh | alter sp [Proc_ReceiverPageFieldSetup] compare minlent and max length and validate change dropdown according to chnage . published in staging
| GMER-152 | Live System Support | 3h | Ganesh | problem: The following transaction with GME no: 80103367308 status is HOLD. Please resend the transaction with the following receiver's name. First name: Нарангэрэл Last name: Чойжил solution : inform to parhlad sir

## 8월 29일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James | 1. Mongolia Test Bank Deposit 2. Implement UI Animation : More enhance ux Recipient List Set up Recipient Send Money Process
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | 1) Dynamic validation successfully tested to Myanmar with payment method bank deposit 2) Dynamic validation successfully tested to Mongolia with payment method bank deposit 3)Dynamic form order changed to :
| GMER-149 | Live System Support(Saroj) | 6h | Saroj | Wrong virtual wallet deposit success at Gme but wallet fail, issue analyze. Purpose of Remit and relationship logic change and changes made in staging and published the changes. Penny test request failed issue identified and resolve the issue. Update the database.
| GMER-150 | Live System Support(Manoj) | 6h | Manoj
| GMER-115 | Dynamic Receiver Setup(API) | 3h | Manoj
| GMER-126 | Exim Bank API | 1d | Ram | Account validation successfully tested through online GME Updated send transaction methods in exim bank api Tested transactions through postman Need to verify the cash transactions at their end Added hidden field in online to find out the
| GMER-152 | Live System Support(Ganesh) | 5h | Ganesh

## 8월 30일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic receiver setup(iOS) | 9h | James
| GMER-117 | Dynamic receiver setup(Android) | 9h | Preyea | Dynamic Validation tested for Payout country Cambodia with Payment Method Cash. Also recipient add/edit/delete process tested for Cambodian Recipient. New and existing translation updated for Mongolia, Uzbek, Russia and Cambodia. Field that are not mandatory i.e. marked “M”, are cleared while updating recipient profile. The reason is explained with the following scenario Problem Scenario : Inconsistent recipient data when not overriding previously inserted data
| GMER-149 | Live System Support(Saroj) | 8h | Saroj
| GMER-150 | Live System Support(Manoj) | 6h | Manoj
| GMER-126 | Exim Bank API | 6h | Ram | Prepared test cases for Transfer To TransferToEIBAccount Transfer To ID of customer other Bank Transfer to Napas Card TransferToEIBCard which nearly took 3 hours Talk with Glenn to clear the confusions related with the api's and
| GMER-152 | Live System Support(Ganesh) | 8h | Ganesh
| GMER-155 | Easy Remit(Core) | 6h | Ganesh | 1. modified form layout and a 2. create easyremit class and add property. 3. create class in data access layer . and add function for register data ( 3. assign value to esayremit class . 4. load valule in all dropwown control (country, native