## 9월2일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. Optimization UI Dynamic Recipient Recipient List 2. Dynamic Recipient Test Myanmar Mongolia Cambodia 3. Shinhan & IBK + Passport Test IBK
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | UI Opitimization and Transaciton Recipient Account field added. Bug fixes related to android phone model Sm-N900K during image inflation process in customer support screen.
| GMER-149 | Live System Support | 5h | Saroj | Analysis of the issue during transaction requested in kakao, skype and email --Checking logs, identifying the bugs and resolving them. Penny test for 2019.08.29 is 40. Bank Deposit has been enabled for Cambodia. Updated the onHold tranaction (approved the success txn and reject the failed txn)
| GMER-25 | Send Txn Process same as web | 3h | Saroj | Made the changes as requested by the mobile api's to adjust. Publish the system and deployed the application.
| GMER-150 | Live System Support | 4h | Manoj | Sunday Support from home form Mongolia TXN resend
| GMER-126 | Exim bank API | 4h | Ram | Started the transaction testing for GME Online but there is no amedment at their end so getting the same unsuccess result as shared in the previous email As there is holiday today on Vietnam, unable to test afterwards Prepared the excel sheet for
| GMER-152 | Live System Support | 3h | Ganesh

## 9월3일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
James
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | Dynamic optional field validation applied to all widget Native country added to add/edit recipient form Testing is due for native country.
| GMER-149 | Live System Support | 1d | Saroj | Wing GME outbound integration discussion. Wing team was asking the problem and I was answering the Quest. Dynamic Receiver Field Setup Excel for Indonesia, Sierra Leone. Tranglo Transaction updated and approved on request by CS team. Penny test Voucher Modification and update for the date 2019-09-01. Hold and Release the transaction upon request by BNI marketing team. Approved the transaction and moved the txn from temp to main to allow CS team to later Cancel the transaction. Changed the logic in Thunes api to address the txn failed cause. Transaction was being rejected even Quotation was created in thunes.
| GMER-150 | Live System Support | 1d | Manoj | 1. Resend Menu Issue in Mongolia 2. Resend Mongolia Hold Transaction 1. Daily Checking Donga Hold Txn Release -toixinloi123@yahoo.com.vn' -buithiphan1578@gmail.com -hoangthilan6879@gmail.com 2.Mongolia Transaction Resend Manually
| GMER-126 | Exim bank API | 6h | Ram | Successfully completed all the transactions through all the available 7 services Account validation successfully validated through online Need to confirm the gateway(way to control the gateway), for now complete the transaction by adding the
| GMER-155 | Easy Remit(Core) | 3h | Ganesh | 1.alter sp for insert data as provide in document. 2. load calendar filed in dob and issuedate 3. test customer registration from easy remit locally .
| GMER-152 | Live System Support | 2h | Ganesh | 1. resend 801283433326 solving steps : inform to majoj sir . and found error while resend txn : "ErrorCode": "1", "Message": "MS03 - Гүйлгээ цуцлагдлаа! " finally inform to kako about issue 2. Negirajendra68@gmail.com can not calcualte

## 9월4일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
James
| GMER-117 | Dynamic Receiver Setup(Android) | 8h | Preyea | Developer side testing completed successfully. APK is available for testing Acceptance Testing. Developer side testing done. Native country field Added to Recipient Add/Edit process. Optional Field handled correctly. Now Testing for mongolia and vietnam.
| GMER-149 | Live System Support | 2h | Saroj
| GMER-25 | Send Txn process same as web | 2h | Saroj | Added the native country in Dynamic Receiver. Changed the Stored Procedure. Changed the List of receiver info, added the parameter during adding and modifying.
| GMER-150 | Live System Support | 1d | Manoj
Ram
| GMER-152 | Live System Support | 2h | Ganesh
| GMER-146 | Cubuana API integration | 3h | Ganesh | communication with cebauna team about gme clabackapi text txn for cash pick up. cebuna need 30 txn so. continue to txn
| GMER-155 | Easy Remit(Core) | 3h | Ganesh | upload document for verfydoc1 and veryfiydoc2 save and display document

## 9월5일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. Add Native Country Field 2. Add Optional Process
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | Dynamic validation logic managed on response to partner routing changed.
Saroj
| GMER-150 | Live System Support | 1d | Manoj | 1. Mongolia TXN Resend 2.Cancel on hold transaction ID 80210074152 3.Kakao Issue -"saisaiko2019@gmail.com Transaction keeps falling since yesterday. Please kindly check" 4. Please check this txn of this customer whether the customer used free
| GMER-126 | Exim Bank API | 6h | Ram | Prepared the testcases for the exim bank api(resend failed transactions) Send the test cases through email Change the configuration for log4net Check the api request/response logs in ApplicationLogger table
Ganesh

## 9월6일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. add isPartnerChanged field -Don't use bank as change partner, mobile side show message 2. Dynamic recipient Test -Indonesia -Mongolia -Bangladesh -India -Myanmar -Vietnam -Nepal
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | End to end testing with setup made by core system.
| GMER-149 | Live System Support | 1d | Saroj | Updated the holded transaction and modified the problematic transaction. Prepare the query for the id number changed of all the customer for an emergency.
| GMER-150 | Live System Support | 1d | Manoj | Cancel on hold transaction ID 80954506619 Request to resend Hold Transaction: 80157932208 request to resend transaction request to resend Re: request to resend Transaction rename and resend request Withdrawal = not sent Update Transaction ID
| GMER-126 | Exim Bank API | 6h | Ram | Added a validation method to validate the send transaction request Added a method in the send transaction and account validation class to set the response Code optimization
| GMER-152 | Live System Support | 2h | Ganesh | 1."W850213n@icloud.com Customer can't send by cash payment" select * from applicationlogger where createby ='W850213n@icloud.com' inform in kakao Rejected for compliance reasons 2.Tarpancirebon@gmail.com cannot transfer to GME wallet Bank

## 9월9일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. changed view logic as add isPartnerChanged parameter 2. For debug, add FLEX module 3. change business logic about fetch recipients
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | Channel IO SDK updated to 6.1.3 Translation for dynamic receiver added for nepal, thailand, bangladesh. *Note -Not all translation are provided in sheets, so only the provided one are updated
| GMER-25 | Send Txn process same as web | 5h | Saroj | Created the sample test data to test the different cases Amend the code and republish and deploy to get the case succeeded. Case checked for Mongolia and Vietnam.
| GMER-150 | Live System Support | 1d | Manoj | 1. Mongolia TXN Resend Manually 2.Update Thunes Txns 3. Cancel Thunes TXns 4. Resolved Kakao Issue 5. Penny Test
| GMER-126 | Exim Bank API | 6h | Ram | Deployment of Exim Bank in UAT Server Started testing AML Scenario provided by Exim Team Added Donga Bank in agentMaster
| GMER-146 | Cebuana API Integration | 4h | Ganesh | communication with cebuna team send transaction for testing but there is issue in cebuna side request solve following issue <PushRemittanceResult xmlns="http://schemas.datacontract.org/2004/07/CebuanaPushRemittanceWCFService"

## 9월10일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. resolved about Exchange Rate 2. changed check payment mode and payment mode id for exist recipient 3. re-release 2.5.0 to app store
| GMER-117 | Dynamic Receiver Setup(Android) | 1d | Preyea | Fixes done with live setup. Deployed to play store.
Saroj
| GMER-150 | Live System Support | 1d | Manoj | 1.Daily Checking 2. Mongolia TXN Resend Manually 3.Update Thunes Txns 4. Cancel Thunes TXns 5. Resolved Kakao Issue 6. Mongolia TXN cancel 7. Dynamic Receiver setup Live Publish and error resolved while testing in live app
| GMER-126 | Exim Bank API | 6h | Ram | Deployed the Gme Online and Exim Bank api Tested the aml scenario provided by exim bank Checked the request and response logs
| GMER-152 | Live System Support | 4h | Ganesh | 1. yapa0584@gmail.com can to send monaey issue : sender last name is missing checking steps :select top 1000 * from Application_Log.dbo.ApplicationLogger(nolock) where createdBy='yapa0584@gmail.com' order by rowId desc

## 9월11일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. Add Native Country Field 2. Add Optional Process
| GMER-93 | Send Txn process same as web(Android) | 1d | Preyea
| GMER-113 | Shinhan, IBK Bank realname verification using KFTC(Android)
Saroj
| GMER-150 | Live System Support | 1d | Manoj | 1.Daily Checking 2. Mongolia TXN Resend Manually 3.Update Thunes Txns 4. Cancel Thunes TXns 5. Resolved Kakao Issue 6. Mongolia TXN cancel 7. Dynamic Receiver setup Live Publish and error resolved while testing in live app
| GMER-126 | Exim Bank API | 5h | Ram | Updated router partner for eximbank for real time testing through online Update branch field in gme online alter table applicationLogger alter column [message] nvarchar(max) null --returning vietnamese msg in success ALTER TABLE CouponSetup ADD usageLimit INT
| GMER-146 | Cebuana API Integration | 1d | Ganesh | integrating cebuna api configuration accounting to UAT credential and endpoint published in UAT test from aut guidelines to test api to QA

## 9월16일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-116 | Dynamic Receiver Setup(iOS) | 1d | James | 1. Add Native Country Field 2. Add Optional Process
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea
| GMER-149 | Live System Support | 1d | Saroj | Developed the report about customer Id type changes made.
| GMER-150 | Live System Support | 1d | Manoj | Live System Support
Ram
| GMER-146 | Cebuana API Integration | 1d | Ganesh | test following transaction in uAT Requesting for a total of 30 test transactions divided among these categories: 5 test transactions below Php50,000 3 test transactions equal to Php50,000 2 test transactions above Php50,000 3 Cancelled

## 9월17일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GK-15 | Balance check using KFTC Open-banking (iOS) | 1d | James
| GK-19 | Zoho people 연동시스템 개발 | 30m | Justin
| GK-20 | JsonRX API문서 개발 | 7h 30m | Justin | 1. mTranskeyServer Issue로 로그인 실패 2. Password 인식문제 3. 코드상 수정 후 우회하여 로그인 → 계정 테스트 4. Function List 작성(모바일 테스트/IOS) - Auth API - Customer API - Receiver API
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea | Basic UI Skeleton defined for domestic transfer module. Started optimization for the cold boot of the app.
| GMER-149 | Live System Support | 1d | Saroj | Sync the statging to uat of the project
Manoj
| GMER-126 | Exim Bank API | 5h | Ram | 1. Prepared test scenario for following: Cash Pick Up EIB Cash Pick Up AML Cash Pick Payout as USD and sent the email for the same 2. Re-setup the service charge, pay commission and mapped accordingly for Exim bank 3. Added the agents for the
| GMER-152 | Live System Support | 2h | Ganesh | 1. patchayapa.phosu@gmail.com transaction error by KJ wallet , new app soution . check apli log found unauthorized transaction check in coupenissue found active . inform to manoj sir.
| GMER-146 | Cebuana API Integration | 6h | Ganesh | 1. followup to cebuna api 2. testing in UAT server 2. API is down in cebuana side . inform to cebuana team

## 9월18일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-149 | Live System Support | 1d | Saroj | Sync the staging to uat of the project - INBOUND PROJECT. CORE. ONLINE TRANSACTIONPROCESSOR MOBILE KJBANK LYHOUR THUNES And Few issue finding of the failed tranasction.
| GMER-150 | Live System Support | 1d | Manoj
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea | Domestic send money form UI created with mocked data
| GMER-155 | Easy Remit(core) | 1d | Ganesh | add customer registration page add List page for approve customer list add isexpired and telephone number fields

## 9월19일(목)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-149 | Live System Support | 1d | Saroj | Merged the inbound Remittance and make it working in UAT after db was sync. Merged the code for inbound Remittance. Create the inbound test agent in the system and configure their service charge and Exchange Rates.
| GMER-150 | Live System Support | 4h | Manoj
| GMER-160 | Partner Reconciliation | 5h | Manoj
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea | Domestic Remittance Send Screen UI fixes and completed. Domestic Txn history UI Completed and integrated with Domestic Remittance Send Screen Password Prompt and OTP Screen successfully integrated with Domestic Remittance Send Screen Validation
| GMER-126 | Exim bank API | 6h | Ram | uat and staging sink of Customer Modification logs report deployment of customer modification logs report in staging code moved from uat to staging regarding exim bank integration deployment of online gme in uat log added in exim api regarding

## 9월20일(금)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-149 | Live System Support | 6h | Saroj | Dynamic receiver issue with Bangladesh and receiver information fixed. SwiftCode updated for Bangladesh banks and tested in UAT. Lyhour Code verification and review started. Agent created in UAT.
| GMER-160 | Partner Reconciliation | 1d | Manoj | UAT Deployment UAT Testing Make Fiel for Live Deployment Live Deployment Reconciliation in live using this menu

## 9월23일(월)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-61 | Lyhour API for Cambodia deposit(Core) | 6h | Saroj | Created the agent and map all the detail required for pushing the transaction to lyhour. Change the api configuration and make a test txn to lyhour. Card transfer module tested for Russia. Also, checked the bank for Bangladesh to route to a specific partner.
| GMER-161 | Synchronize inbound process to UAT/Staging |  | Manoj
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea
| GMER-126 | Exim bank API | 6h | Ram | UAT testing of Exim bank api Prepared the test cases for special scenario provided by exim team and forward the email for the same Deployment of UAT Gme online

## 9월24일(화)
Type | No | Issue | 작업시간 | 담당자 | 내용
| GMER-61 | Lyhour API for Cambodia deposit(Core) | 5h | Saroj | Created the Prince Bank Agent in UAT for testing purpose and make the necessary configuration.
| GMER-150 | Live System Support | 4h | Manoj | Partner Reconciliation file upload and synchronize transaction Update Cambodia txn Cancel Mongolia Transactions Kakao issue resolved Daily checking
| GMER-161 | Synchronize Inbound process to UAT/Staging | 5h | Manoj | Update sps and logic mismatch during synchronize project file synchronize svn issue still not solved deploy staging project file to uat for testing scheduler run successfully registration successfully bypass penny request for the test
| GMER-73 | Domestic bank transfer using KFTC(Android) | 1d | Preyea
| GMER-126 | Exim bank API | 6h | Ram | Created sp: PROC_EXIM_ACCOUNT_INFORMATION Updated sp: PROC_PROCESS_TRAN_EXIM Created a method to fetch the account information using bankId Use the agentmaster payOption field to distinguish the gateway. 1 indicates EIB gateway and 2 indicates

## 9월25일(수)
Type | No | Issue | 작업시간 | 담당자 | 내용