## Sheet1
Project Name | SN | Tasks | Achievement | Remarks
GME Korea Core/ Onine | 1 | Inbound 2nd Phase | 100 | Deployed in Staging
| 2 | Shinhan/IBK Bank using KFTC | 100 | publish done
| 3 | Dynamic Receiver Setup | 100 | publish done
| 4 | Send Txn process same as web | 100 | publish done
| 5 | Auto-remit using KJ multiple-accounts | 10 | In Progress
| 6 | Check existing KFTC Service with Open banking | 70 | In Progress
| 7 | Balance check using KFTC Open-Flatform | 100 | publish done
| 8 | Auto refund using KFTC Open-Flatform | 100 | publish done
| 9 | Domestic bank transfer using KFTC Open-Flatform | 100 | publish done
| 10 | Micro Loan | 0 | In Progress
| 11 | Reward/Coupon 2nd Phase | 0 | In Progress
| 12 | NI Bank cancel-transaction from Core system | 100 | publish done
Project Name | SN | Tasks | Achievement | Remarks
GME Korea Mobile App and API | 1 | Shinhan/IBK Bank using KFTC | 90 | Publish done
| 2 | Dynamic Receiver Setup | 90 | Publish done
| 3 | Send Txn process same as web | 90 | Publish done
| 4 | Auto-remit using KJ multiple-accounts | 10 | In progress
| 5 | Check existing KFTC Service with Open banking | 70 | In progress
| 6 | Balance check using KFTC Open-Flatform | 100 | Publish done
| 7 | Auto refund using KFTC Open-Flatform | 100 | Publish done
| 8 | Domestic bank transfer using KFTC Open-Platform | 100 | Publish done
| 9 | Micro Loan | 0 | In progress
| 10 | Reward/Coupon 2nd Phase | 0 | In progress
| 11 | Exim bank | 90 | Deployed in Staging
| 12 | Calcurate in first screen | 100 | Publish done
| 13 | Lyhour API for Cambodia deposit | 90 | Deployed in Staging
| 14 | K Bank API | 100 | Publish done
| 15 | Cebuana API | 90 | Deployed in Staging
| 16 | Card(Visa, Master) transfer | 100 | Publish done