## Q3 IT Project
Category | SN | Project Code (Name) | Description | PIC | Developer | Start Date | End Date | Incentive
Ongoing |  | [2005-04] FSOS-API | FSOS API | Pralhad | Ram & Chetan
|  | [2005-05] CB Bank API | CB Bank API | Pralhad | Ganesh & Chetan
|  | [2006-07] Portal upgrade | Provide Portal to Kyodai and other partners( partner should see settlement report and search the txn status) | Pralhad | Saroj | ING
|  | [2005-06] Nepal Realtime bank deposit | Nepal Realtime bank deposit | Pralhad | Ram
|  | [2005-07] Re-process hold txn | Re-process hold txn of Contact, Lyhour, Agrani, BNI, DongA, EXIM | Pralhad | Saroj
|  | [2005-08] System Optimization | System optimization working together with SWIFT Nepal | Max and Pralhad | SWIFT
|  |  | Inbound Fx Calculation | Pralhad | Pralhad
Stabilization of GME Service | 1 | [2005-01] Stabilization of domestic txn | Even domestic Transfer success from wallet it show Error 404 at last - Need to Fix this issue | Max |  |  | 2020-08-20 | 50000
| 2 | [2005-02] Limit amount on domestic txn | Domestic transaction and Withdraw should be failed from our side if customer try to send money more than KRW 6.5 Mil( Dont allowe Customer To send more than 6.5 Mil) | Max |  |  |  | 50000
| 3 | [2005-10] Exim bank | Exim Bank transaction have to make real time 24/7-Vietnam | Pralhad |  | ING |  | 50000
| 4 | [2005-11] Id visible in core system | Email id and user id both should be visible in Core system | Pralhad |  |  |  | 50000
| 5 | [2005-12] Primary-Secondary id visible in core system | Primary id card and secondary Id card both details Visible in Core system | Pralhad |  |  |  | 50000
| 6 | [2005-13] IME Cash Payment | Change Cash Payment Naming to Cash payment (IME)- Nepal Corridor Issue | Pralhad |  |  |  | 50000
| 7 | [2005-14] IME Wallet Payment | Change Mobile Wallet Naming to IME Pay Wallet- Nepal Corridor Issue | Pralhad |  |  |  | 50000
| 8 |  | Change the label for Mobile app a)While selecting wallet as payout Mode Instead Select Bank Change to "Select Wallet" b)Bank Account Number Change To "Mobile Wallet Number" | Pralhad |  |  |  | 50000
| 9 |  | If Money Was deducted from customer Auto Debit and txn failed and money refunded to GME wallet , then there should be admin menu to check failed txn country wise | Pralhad |  |  |  | 50000
| 10 |  | Non KYC customer list Should be Editable | Pralhad |  |  |  | 50000
| 11 | [2006-07] Islami bank API | Re activate Islami bank validation. - Bangladesh Corridor Issue | Pralhad |  | ING |  | 50000
| 12 |  | Rocket wallet problem;-successful transaction failed when we do 2nd transaction in same details- Bangladesh Corridor Issue | Pralhad |  |  |  | 50000
| 13 |  | Run status update sequence every 10 minutes for sri Lanka-Sri Lanka Corridor | Pralhad |  |  |  | 50000
| 14 |  | The exchange rate calculation for Mongolia is slow for Contact-Mongolia Corridor | Pralhad |  |  |  | 50000
| 15 |  | Solve the Qiwi Bank "Contact" Timeout issue | Max |  |  |  | 50000
| 16 |  | While doing local top up we have to select view balance 1st otherwise we can't process top up- Need to Fix the issue | Max |  |  |  | 50000
| 17 |  | Filter KFTC customer by customer user id and Expiry date | Pralhad |  |  |  | 50000
| 18 |  | Filter Customer by Id Expiry Date | Pralhad |  |  |  | 50000
| 19 |  | In Security Keyboard : last step in Transaction complete change label to OK | Max |  |  | 2020-08-05 | 50000
| 20 |  | Highlight Select Languages button in android phone | Pralhad |  |  |  | 50000
| 21 |  | Fix the Zoho people issue with the server connection | Max |  |  |  | 50000
New Development | 22 |  | Moneygram API | Pralhad |  |  |  | 300000
| 23 | [2004-01] Reward Point-Coupon 2nd Phase | Reward Coupon 2nd Phase | Max | Max, JY |  | 2020-05-29 | 300000
| 24 | [2004-02] Allow Customer to Change Certain field | Allow Customers to Edit their Profile | Max | Max, JY |  | 2020-05-29 | 100000
| 25 | [2006-05] Simplifying the new registration | Simplifying the New Registration process by removing "Add auto Debit " and allow customer to login even without incomplete information | Subash |  |  |  | 500000
| 26 |  | Admin Menu to hold realtime Txn | Pralhad |  |  |  | 500000
| 27 | [2005-03] Easy Remit with Korea-Seven | Easy Remit using LOTTE ATM | Max |  |  |  | 500000
| 28 |  | International Top-up from Tranglo | Pralhad |  |  |  | 100000
| 29 |  | Menu icon should be with name MENU | Pralhad |  |  | 2020-08-20 | 50000
| 30 |  | Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | Pralhad |  |  |  | 50000
| 31 | [2008-16] Set Schedule for Push Notification | Set Schedule for Push Notification | Max |  |  |  | 50000
| 32 | [2008-18] History for Push Notification | History for push notification | Max
| 33 |  | push notification with picture and links. | Max |  |  |  | 50000
| 34 |  | Location Based Push notification | Max |  |  |  | 50000
| 35 |  | Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Max |  |  |  | 50000
| 36 |  | Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | Max |  |  |  | 50000
| 37 | [2008-15] Transaction Details look up using KFTC API | Transaction Details lookup using KFTC API | Max |  |  |  | 200000
| 38 | [2008-02] Downloadable in PDF File | Customer Statement downloadable in pdf from GME app | Max |  |  |  | 100000
| 39 |  | Customers Contact mining and inviting Customers Contact to join GME App and send invitation or push message using kakaotalk | Max |  |  |  | 500000
| 40 |  | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | Max |  |  |  | 500000
| 41 |  | Block/Unblock Easy remit service by Admin User without needing IT support | Max |  |  |  | 50000
| 42 |  | New individual referral code for everyone | Max |  |  |  | 50000
| 43 |  | Make it possible to send bulk emails from the system | Pralhad |  |  |  | 50000
| 44 |  | Admin Menu to send Bulk SMS | Max |  |  |  | 50000
| 45 |  | All Branch Tellers to be able to login to different branch with single login ID | Pralhad |  |  |  | 50000
| 46 |  | Uremit API | Pralhad |  |  |  | 100000
| 47 |  | NIUM API | Pralhad |  |  |  | 100000
| 48 |  | Online sim card Apply registration form in APP |  |  |  |  | 100000
| 49 |  | Online loan development together with online electronic Signature | Max |  |  |  | 500000
| 50 |  | Galaxia coupon service with Hyosung | Max |  |  |  | 200000
| 51 |  | Capability to give country specific report according to native country of Admin user | Pralhad |  |  |  | 500000
| 52 | [2005-15] Security inspection of GME |  | Max
| 53 | [2005-16] Change G/W for KFTC | Change G/W for KFTC | Max | Max | 2020-05-01 | 2020-05-21
| 54 | [2005-18] Chinese translation in Mobile App |  | Max | JB, Preyea | 2020-05-26 | 2020-06-04
| 55 | [2005-19] Chinese translation in Online
| 56 | [2006-01] Card Payment API in Koronapay
| 57 | [2006-02] Direct Wallet Topup in IME Pay
| 58 | [2006-03] Verification of Country code for Flag
| 59 | [2006-04] Apply of return claim
| 60 | [2006-10] Wing Realtime bank deposit API Integration | Wing Realtime Bank deposit API Integration |  |  | ING
| 61 | [2006-09] Card payment from Thunes | Starting Australia and Uzbekistan card payment from Thunes |  |  | ING
| 62 | [2007-15] Check duplicate notification in Easy-Remit | Check duplicate notifications and reject them if duplicate notifications occur.
| 63 | Giftcon Service | Provides services for customers to use Giftcon
| 64 | [2007-18] Korea-Seven 2nd Phase | All customer can using Lotte ATM | Max |  |  | 2020-08-12
| 65 | [2008-01] Fixed bugs reported in Firebase Crashlytics |  | Max
| 66 | [2008-03] Change title in Virtual Keypad | Change to 'OK' from 'COMPLETE' in Virtual Keypad | Max |  |  | 2020-08-12
| 67 | [2008-04] Secondary ID Document Display | Customer secondary id document display problem in core system | Max |  |  | 2020-08-12
| 68 | [2008-06] Domestic Txn for wallet to wallet | IT is transfer money from a wallet account to a wallet account | Max |  |  | 2020-08-20
| 69 | [2008-07] Change Online Register | Change Online Register from Powercall Request
| 70 | [2008-08] Modification Inbound Transaction | Modification Inbound Transaction from core system
| 71 | [2008-09] Bank Deposit for Singapore and Malaysia from Thunes | Bank Deposit for Singapore and Malaysia from Thunes
| 72 | [2008-10] Notification on Mobile Update | The ability to notify customers when there is an important update, and the customer needs to update. | Max
| 73 | [2008-11] Change Sender/Receiver Naming Rule on MoneyGram API | Change sender/receiver naming rule firstName = firstName + middleName(if not null) lastName = lastName1 + lastName2(if not null) |  |  |  | 2020-08-26
| 74 | [2008-12] Report according to Native country
| 75 | [2008-13] Change the permissions of a branch account
| 76 | [2008-14] Realtime bank deposit from Kbank
| 77 | [2008-19] Collect of mobile phone contact | The ability to collect and store registered contacts on the customer's mobile phone in the DB.
| 78 | [2008-21] TerraPay API | TerraPay API
| 79 | [2008-20] DTOne API | International Top-up from DTOne
| 80 | 신용관리(계좌관리) 프로젝트
| 81 | 핸드폰번호를 이용한 국내송금
Other Projects | 82 | [2007-19] Setup for In-house Banking System | In-house banking integration with Hana bank | Max |  |  |  | 300000
| 83 | [2005-17] 선불전자지급수단 발행및 관리업 라이선스 | E-PrePayment License | Max |  |  | 2020-08-21 | 500000
| 84 |  | AML and STR reporting system developing |  |  |  |  | 500000
| 85 |  | Develop the HR System for attendance, punctuality, annual leave, Payroll calculation |  |  |  |  | 2000000
| 86 |  | Bank of Korea Reporting through Fintech Association System API |  |  |  |  | 500000
| 87 |  | Integrate ERP with our System( GME Finance Crizen System) | Max |  |  |  | 300000
| 88 | [2007-11] GME System Consulting | GME System Consulting | Max
| 89 | [2007-10] Setup GitHub | Setup GitHub | Max
| 90 | [2007-04] Sepatate IIS Server | Separating WEB with WEB and WAS | Max |  |  | 2020-08-05
| 91 | [2006-14] DB Encryption | DB Encryption using Symmetric Key(AES-256) | Max |  |  | 2020-08-05
| 92 | [2009-01] System Monitoring and Send SMS | It is the ability to send a warning message when something unusual occurs during system surveillance. | Max
| 93 | [2007-13] Manual for Admin Page
| 94 | [2007-14] Open-Banking API | Change of API parameters for open banking-withdraw |  |  |  | 2020-07-31
| 95 | [2008-17] Mobile App Tracking on Firebase | Mobile App Tracking on Firebase
| 96 |  | GME Pay solution enhancing and doing API with local partners | Max |  |  |  | 1000000
| 97 | [2006-15] GME Pay App | GME Pay App | Max |  |  | 2020-08-05
System/Infra | 98 | [2006-13] GME System Upgrade Plan | GME System Upgrade Plan | Max
| 99 | [2007-02] DB Redundancy | DB Redundancy | Max
| 100 | [2007-03] DB Access Control | DB Access Control | Max
| 101 | [2007-05] Setup Firewall | Firewall Setup at HQ | Max |  |  | 2020-08-05
| 102 | [2007-06] Setup NAC | NAC Setup at HQ | Max |  |  | 2020-08-05
| 103 | [2007-07] Setup Vaccine | Vaccine Setup at HQ | Max |  |  | 2020-08-05
| 104 | [2007-08] Setup IPSEC VPN | IPSEC VPN Setup at HQ and FSDC | Max |  |  | 2020-08-05
| 105 | [2007-09] Setup VPN Redundancy | Operational VPN Redundancy Setup | Max
| 106 | [2007-16] Setup NTP |  |  |  |  | 2020-08-05
| 107 | [2008-05] 금융보안원 기업보안점검
| 108 | [2008-F01] DB Migration | DB Migration
| 109 | [2008-F02] 이용기관점검 from 금융보안원
| 110 | [2009-F01] Setup FTP in DB
| 111 | [2009-F02] E-Prepayment License 리스트 작성
Supplement |  | [2008-E01] Change Fingerprint Logic | Fingerprint error in last step of transaction, even after put the correct password, message will say OTP IS WRONG |  |  |  | 2020-08-19
|  | [2008-E02] ChannelTalk SDK Update | 채널톡에서 SDK를 업데이트해서, 이미지가 안보이는 현상을 보완 |  |  |  | 2020-08-19
|  |  | Total |  |  |  |  | 11800000

## Q3 IT Project (2)
Group | Category | SN | Project Code (Name) | Description | PIC | Developer | Start Date | End Date | Incentive
| Ongoing |  | [2005-04] FSOS-API | FSOS API | Pralhad | Ram & Chetan
|  |  | [2005-05] CB Bank API | CB Bank API | Pralhad | Ganesh & Chetan
|  |  | [2006-07] Portal upgrade | Provide Portal to Kyodai and other partners( partner should see settlement report and search the txn status) | Pralhad | Manoj/Ganesh
|  |  | [2005-06] Nepal Realtime bank deposit | Nepal Realtime bank deposit | Pralhad | Ram
|  |  | [2005-07] Re-process hold txn | Re-process hold txn of Contact, Lyhour, Agrani, BNI, DongA, EXIM | Pralhad | Saroj
|  |  | [2005-08] System Optimization | System optimization working together with SWIFT Nepal | Max and Pralhad | SWIFT
|  | 1 |  | Inbound Fx Calculation | Pralhad | Pralhad | Ongoing
Issue | Online | 2 | [2009-03] Renewal for GME Online | Renewal for GME Online | Max | Summer |  | 2020-09-11
| Core | 3 | [2008-04] Secondary ID Document Display | Customer secondary id document display problem in core system | Max |  |  | 2020-08-12
|  | 4 | [2008-08] Modification Inbound Transaction | Modification Inbound Transaction from core system | Pralhad | Manoj/Ganesh
|  | 5 | [2008-13] Change the permissions of a branch account
| Mobile | 6 | [2005-01] Stabilization of domestic txn | Even domestic Transfer success from wallet it show Error 404 at last - Need to Fix this issue | Max |  |  | 2020-08-20
|  | 7 |  | Change the label for Mobile app a)While selecting wallet as payout Mode Instead Select Bank Change to "Select Wallet" b)Bank Account Number Change To "Mobile Wallet Number" | Pralhad |  |  |  | 50000
|  | 8 |  | Menu icon should be with name MENU | Pralhad |  |  | 2020-08-20 | 50000
|  | 9 |  | While doing local top up we have to select view balance 1st otherwise we can't process top up- Need to Fix the issue | Max |  |  |  | 50000
|  | 10 | [2008-03] Change title in Virtual Keypad | Change to 'OK' from 'COMPLETE' in Virtual Keypad | Max |  |  | 2020-08-12
|  | 11 |  | Highlight Select Languages button in android phone | Pralhad | Preyea |  |  | 50000
| API | 12 | [2006-07] Islami bank API | Re activate Islami bank validation. - Bangladesh Corridor Issue | Pralhad | Saroj/Ram |  |  | 50000
|  | 13 |  | Rocket wallet problem;-successful transaction failed when we do 2nd transaction in same details- Bangladesh Corridor Issue | Pralhad |  |  |  | 50000
|  | 14 |  | Moneygram API | Pralhad |  |  |  | 300000
|  | 15 |  | Solve the Qiwi Bank "Contact" Timeout issue | Max |  |  |  | 50000
|  | 16 | [2007-15] Check duplicate notification in Easy-Remit | Check duplicate notifications and reject them if duplicate notifications occur.
|  | 17 | [2007-Add03] - [MoneyGram] Review and update September release |  |  | Saroj
|  | 18 | [2008-Exim]-Transactions Automatically Route Request from Exim to Donga |  |  | Manoj
|  | 19 | [2009-01]-Sacom bank: Cash/Bank/Home delivery API |  |  | Saroj
|  | 20 | [2009-02]- Seperate Relationship list from Oversear Txn |  |  | Saroj
|  | 21 | [2009-04]-Seperate Real time API for GIBL Bank |  |  | Saroj
|  | 22 | [2009-06]-Real time service for IMEPay Wallet |  |  | Manoj
| Others | 23 | [2005-02] Limit amount on domestic txn | Domestic transaction and Withdraw should be failed from our side if customer try to send money more than KRW 6.5 Mil( Dont allowe Customer To send more than 6.5 Mil) | Max
|  | 24 | [2005-13] IME Cash Payment | Change Cash Payment Naming to Cash payment (IME)- Nepal Corridor Issue | Pralhad |  |  |  | 50000
|  | 25 | [2005-14] IME Wallet Payment | Change Mobile Wallet Naming to IME Pay Wallet- Nepal Corridor Issue | Pralhad |  |  |  | 50000
|  | 26 |  | The exchange rate calculation for Mongolia is slow for Contact-Mongolia Corridor | Pralhad |  |  |  | 50000
|  | 27 | [2007-Add01] Rocket Wallet Txn success but goto Agrani in New App
|  | 28 | [2007-Add02] - Customer Balance Mismatch and adjustment
|  | 29 | [2007-Add04] - Cannot move account Ledger
|  | 30 | [2007-Add05] - USD amt and Usd Rate not updated
|  | 31 | [2007-Add06] - New Compliance Rule for Nigeria
|  | 32 | Development for Missing Country flags
|  | 33 | Allow to edit State/district missing home delivery Txn
|  | 34 | [2008]-combine the inbound ledger for inbound and outbound
|  | 35 | [2008]-Change Calender for all accounting menus
|  | 36 | [2007] -KoronaPay : Status Update for Card Payment
|  | 37 | [2007]-Android Front Layout prepared same as iOS
|  | 38 | [Wing] Update Old duplicate control no
|  | 39 | Update missing country flags in website and Mobile App
|  | 40 | [2008]-Allow admin to modify the Temp transaction
|  | 41 | [2008]-Inbound Transaction from Payportal
|  | 42 | [2008-Error02]- MoneyGram: Put commit failed tarnsaction on Hold
|  | 43 | [2008]- MoneyGram : Send sender and receiver full name from API
|  | 45 | [2008-Thunes]- Allow fullname to send transaction
|  | 46 | [2008-MoneyGram]-Allow to send Optional name value/Add TT for API failed Txn
|  | 47 | [2008]- Report to check Failed Autodebit/wallet Txn
|  | 48 | [2008]-Auto stop scheduler for KBank INSUFFICIENT FUND transaction
|  | 49 | [2008-CommercialBank]-Valid Mobile format for SMS Notification to Receiver
|  | 50 | [2009-05]-Real time service for GME Nepal Bank Deposit
New Project | Online | 51 | [2005-19] Chinese translation in Online
| Core | 52 | [2005-11] Id visible in core system | Email id and user id both should be visible in Core system | Pralhad
|  | 53 | [2005-12] Primary-Secondary id visible in core system | Primary id card and secondary Id card both details Visible in Core system | Pralhad |  |  |  | 50000
|  | 54 |  | If Money Was deducted from customer Auto Debit and txn failed and money refunded to GME wallet , then there should be admin menu to check failed txn country wise | Pralhad | Ganesh |  |  | 50000
|  | 55 |  | Non KYC customer list Should be Editable | Pralhad | Ram |  |  | 50000
|  | 56 |  | Run status update sequence every 10 minutes for sri Lanka-Sri Lanka Corridor | Pralhad | Saroj |  |  | 50000
|  | 57 |  | Filter KFTC customer by customer user id and Expiry date | Pralhad |  |  |  | 50000
|  | 58 |  | Filter Customer by Id Expiry Date | Pralhad |  |  |  | 50000
|  | 59 |  | Admin Menu to hold realtime Txn | Pralhad |  |  |  | 500000
|  | 60 | [2008-16] Set Schedule for Push Notification | Set Schedule for Push Notification | Max |  |  | 2020-09-11 | 50000
|  | 61 | [2008-18] History for Push Notification | History for push notification | Max |  |  | 2020-09-11
|  | 62 | [2009-10] Image Push Notification | push notification with picture and links. | Max |  |  |  | 50000
|  | 63 |  | Location Based Push notification | Max |  |  |  | 50000
|  | 64 | 모바일앱을 다운로드했지만, 가입하지 않는 고객에 대한 Push | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | Max |  |  |  | 500000
|  | 65 |  | Block/Unblock Easy remit service by Admin User without needing IT support | Max |  |  |  | 50000
|  | 66 |  | Make it possible to send bulk emails from the system | Pralhad | Saroj/Ram |  |  | 50000
|  | 67 |  | Admin Menu to send Bulk SMS | Pralhad | Saroj/Ram |  |  | 50000
|  | 68 |  | All Branch Tellers to be able to login to different branch with single login ID | Pralhad | Manoj/Ganesh |  |  | 50000
|  | 69 |  | Capability to give country specific report according to native country of Admin user | Pralhad | Manoj/Ganesh |  |  | 500000
|  | 70 | [2006-04] Apply of return claim
|  | 71 | [2008-12] Report according to Native country
| Mobile | 72 | [2004-01] Reward Point-Coupon 2nd Phase | Reward Coupon 2nd Phase | Max | Max, JY |  | 2020-05-29 | 300000
|  | 73 | [2004-02] Allow Customer to Change Certain field | Allow Customers to Edit their Profile | Max | Max, JY |  | 2020-05-29 | 100000
|  | 74 | [2006-05] Simplifying the new registration | Simplifying the New Registration process by removing "Add auto Debit " and allow customer to login even without incomplete information | Subash |  |  |  | 500000
|  | 75 | [2005-03] Easy Remit with Korea-Seven | Easy Remit using LOTTE ATM | Max |  |  |  | 500000
|  | 76 |  | International Top-up from Tranglo | Pralhad |  |  |  | 100000
|  | 77 |  | Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | Pralhad |  |  |  | 50000
|  | 78 |  | Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Max | Andrew |  |  | 50000
|  | 79 |  | Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | Max | Andrew |  |  | 50000
|  | 80 | [2008-15] Transaction Details look up using KFTC API | Transaction Details lookup using KFTC API | Max |  |  | 2020-09-23 | 200000
|  | 81 | [2008-02] Downloadable in PDF File | Customer Statement downloadable in pdf from GME app | Max |  |  | 2020-09-23 | 100000
|  | 82 |  | Customers Contact mining and inviting Customers Contact to join GME App and send invitation or push message using kakaotalk | Max |  |  |  | 500000
|  | 83 |  | Online sim card Apply registration form in APP |  | Summer |  |  | 100000
|  | 84 | Deposit Money from Convenience Store | A service that allows you to deposit money from convenience store with Galaxia | Max |  |  |  | 200000
|  | 85 | Giftcon Service | Gifticon service using virtual account with Galaxia | Max
|  | 86 | Deposit Money from All ATMs | Service to deposit money from ATM | Max
|  | 87 | KJ Bank Firm banking Service | Service to virtual account using the firm banking of KJ-Bank | Max
|  | 88 | [2005-18] Chinese translation in Mobile App |  | Max | JB, Preyea | 2020-05-26 | 2020-06-04
|  | 89 | [2006-03] Verification of Country code for Flag
|  | 90 | [2007-18] Korea-Seven 2nd Phase | All customer can using Lotte ATM | Max |  |  | 2020-08-12
|  | 91 | [2008-01] Fixed bugs reported in Firebase Crashlytics |  | Max
|  | 92 | [2008-06] Domestic Txn for wallet to wallet | IT is transfer money from a wallet account to a wallet account | Max |  |  | 2020-08-20
|  | 93 | [2008-10] Notification on Mobile Update | The ability to notify customers when there is an important update, and the customer needs to update. | Max |  |  | 2020-09-23
|  | 94 | [2008-19] Collect of mobile phone contact | The ability to collect and store registered contacts on the customer's mobile phone in the DB.
|  | 95 | 핸드폰번호를 이용한 국내송금
|  | 96 | [2009-07] Adding Permission for Mobile App | Add location, storage, phone, address book, camera permissions
|  |  | [2009-08] Success message is printed when purchasing coupons | 거래내역조회를 할수 있는 쿠폰을 구매하는데 성공하면 출력하는 메시지를 변경
| API | 97 | [2008-21] TerraPay API | TerraPay API | Max
|  | 98 | [2008-20] DTOne API | International Top-up from DTOne | Max
|  | 99 | [2009-09] AliPay API | AliPay API | Max
|  | 100 | [2005-10] Exim bank | Exim Bank transaction have to make real time 24/7-Vietnam | Pralhad
|  | 101 |  | Uremit API | Pralhad |  |  |  | 100000
|  | 102 |  | NIUM API | Pralhad |  |  |  | 100000
|  | 103 | [2006-01] Card Payment API in Koronapay
|  | 104 | [2006-02] Direct Wallet Topup in IME Pay
|  | 105 | [2008-09] Bank Deposit for Singapore and Malaysia from Thunes | Bank Deposit for Singapore and Malaysia from Thunes
|  | 106 | [2006-10] Wing Realtime bank deposit API Integration | Wing Realtime Bank deposit API Integration | Pralhad | Saroj | Ongoing
|  | 107 | [2006-09] Card payment from Thunes | Starting Australia and Uzbekistan card payment from Thunes
|  | 108 | [2008-14] Realtime bank deposit from Kbank |  |  | Manoj | Ongoing
| Others | 109 |  | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | Max |  |  |  | 500000
|  | 110 |  | Fix the Zoho people issue with the server connection | Max |  |  |  | 50000
|  | 111 |  | New individual referral code for everyone | Max |  |  |  | 50000
|  | 112 |  | Online loan development together with online electronic Signature | Max |  |  |  | 500000
|  | 113 | [2005-16] Change G/W for KFTC | Change G/W for KFTC | Max | Max | 2020-05-01 | 2020-05-21
|  | 114 | [2008-11] Change Sender/Receiver Naming Rule on MoneyGram API | Change sender/receiver naming rule firstName = firstName + middleName(if not null) lastName = lastName1 + lastName2(if not null) |  |  |  | 2020-08-26
|  | 115 | 신용관리(계좌관리) 프로젝트
|  | 116 | [2007-19] Setup for In-house Banking System | In-house banking integration with Hana bank | Max |  |  |  | 300000
|  | 117 | [2005-17] 선불전자지급수단 발행및 관리업 라이선스 | E-PrePayment License | Max |  |  | 2020-08-21 | 500000
|  | 118 |  | AML and STR reporting system developing |  |  |  |  | 500000
|  | 119 |  | Develop the HR System for attendance, punctuality, annual leave, Payroll calculation |  |  |  |  | 2000000
|  | 120 |  | Bank of Korea Reporting through Fintech Association System API |  |  |  |  | 500000
|  | 121 |  | Integrate ERP with our System( GME Finance Crizen System) | Max |  |  |  | 300000
|  | 122 | [2007-11] GME System Consulting | GME System Consulting | Max
|  | 123 | [2007-10] Setup SVN in Korea | Setup SVN in Korea | Max
|  | 124 | [2007-04] Sepatate IIS Server | Separating WEB with WEB and WAS | Max |  |  | 2020-08-05
|  | 125 | [2006-14] DB Encryption | DB Encryption using Symmetric Key(AES-256) | Max |  |  | 2020-08-05
|  | 126 | [2009-01] System Monitoring and Send SMS | It is the ability to send a warning message when something unusual occurs during system surveillance. | Max
|  | 127 | [2007-13] Manual for Admin Page
|  | 128 | [2007-14] Open-Banking API | Change of API parameters for open banking-withdraw |  |  |  | 2020-07-31
|  | 129 | [2008-17] Mobile App Tracking on Firebase | Mobile App Tracking on Firebase
|  | 130 |  | GME Pay solution enhancing and doing API with local partners | Max |  |  |  | 1000000
|  | 131 | [2006-15] GME Pay App | GME Pay App | Max |  |  | 2020-08-05
|  | 132 | [2009-02] Other development | 1) 포인트 상품 리스트에서 스피커를 삭제 2) 해외/국내 송금 영수증 화면에 송금시간을 추가 3) 해외/국내 송금 영수증 화면에 보낸사람이름을 추가 4) 국내송금에서 송금받는 계좌번호를 숫자로만 입력(iOS)
| System/Infra | 132 | [2005-15] Security inspection of GME |  | Max
|  | 133 | [2006-13] GME System Upgrade Plan | GME System Upgrade Plan | Max
|  | 134 | [2007-02] DB Redundancy | DB Redundancy | Max
|  | 135 | [2007-03] DB Access Control | DB Access Control | Max
|  | 136 | [2007-05] Setup Firewall | Firewall Setup at HQ | Max |  |  | 2020-08-05
|  | 137 | [2007-06] Setup NAC | NAC Setup at HQ | Max |  |  | 2020-08-05
|  | 138 | [2007-07] Setup Vaccine | Vaccine Setup at HQ | Max |  |  | 2020-08-05
|  | 139 | [2007-08] Setup IPSEC VPN | IPSEC VPN Setup at HQ and FSDC | Max |  |  | 2020-08-05
|  | 140 | [2007-09] Setup VPN Redundancy | Operational VPN Redundancy Setup | Max
|  | 141 | [2007-16] Setup NTP |  |  |  |  | 2020-08-05
|  | 142 | [2008-05] 금융보안원 기업보안점검
|  | 143 | [2008-F01] DB Migration | DB Migration
|  | 144 | [2008-F02] 이용기관점검 from 금융보안원
|  | 145 | [2009-F01] Setup FTP in DB
|  | 146 | [2009-F02] E-Prepayment License 리스트 작성
| Supplement | 147 | [2008-E01] Change Fingerprint Logic | Fingerprint error in last step of transaction, even after put the correct password, message will say OTP IS WRONG |  |  |  | 2020-08-19
|  | 148 | [2008-E02] ChannelTalk SDK Update | 채널톡에서 SDK를 업데이트해서, 이미지가 안보이는 현상을 보완 |  |  |  | 2020-08-19
|  |  |  | Total |  |  |  |  | 5700000
Auto remit with Korea-Seven
KJ Bank 입금에러에 대한 원인
AliPay API