## 2020-Q3
Group | Category | SN | Project Code (Name) | Description | PIC | Developer | Start Date | End Date | Incentive
| Ongoing |  | [2005-04] FSOS-API | FSOS API | Pralhad | Ram & Chetan
|  |  | [2005-05] CB Bank API | CB Bank API | Pralhad | Ganesh & Chetan
|  |  | [2006-07] Portal upgrade | Provide Portal to Kyodai and other partners( partner should see settlement report and search the txn status) | Pralhad | Manoj/Ganesh
|  |  | [2005-06] Nepal Realtime bank deposit | Nepal Realtime bank deposit | Pralhad | Ram
|  |  | [2005-07] Re-process hold txn | Re-process hold txn of Contact, Lyhour, Agrani, BNI, DongA, EXIM | Pralhad | Saroj
|  |  | [2005-08] System Optimization | System optimization working together with SWIFT Nepal | Max and Pralhad | SWIFT
|  | 1 |  | Inbound Fx Calculation | Pralhad | Pralhad | Ongoing
Issue | Online | 2 | [2009-03] Renewal for GME Online | Renewal for GME Online | Max | Summer |  | 2020-09-11
| Core | 3 | [2008-04] Secondary ID Document Display | Customer secondary id document display problem in core system | Max |  |  | 2020-08-12
|  | 4 | [2008-08] Modification Inbound Transaction | Modification Inbound Transaction from core system | Pralhad | Manoj/Ganesh
|  | 5 | [2008-13] Change the permissions of a branch account
| Mobile | 6 | [2005-01] Stabilization of domestic txn | Even domestic Transfer success from wallet it show Error 404 at last - Need to Fix this issue | Max |  |  | 2020-08-20
|  | 7 |  | Change the label for Mobile app a)While selecting wallet as payout Mode Instead Select Bank Change to "Select Wallet" b)Bank Account Number Change To "Mobile Wallet Number" | Pralhad |  |  |  | 50000
|  | 8 |  | Menu icon should be with name MENU | Pralhad |  |  | 2020-08-20 | 50000
|  | 9 |  | While doing local top up we have to select view balance 1st otherwise we can't process top up- Need to Fix the issue | Max |  |  |  | 50000
|  | 10 | [2008-03] Change title in Virtual Keypad | Change to 'OK' from 'COMPLETE' in Virtual Keypad | Max |  |  | 2020-08-12
|  | 11 |  | Highlight Select Languages button in android phone | Pralhad | Preyea |  |  | 50000
| API | 12 | [2006-07] Islami bank API | Re activate Islami bank validation. - Bangladesh Corridor Issue | Pralhad | Saroj/Ram |  |  | 50000
|  | 13 |  | Rocket wallet problem;-successful transaction failed when we do 2nd transaction in same details- Bangladesh Corridor Issue | Pralhad |  |  |  | 50000
|  | 14 |  | Moneygram API | Pralhad |  |  |  | 300000
|  | 15 |  | Solve the Qiwi Bank "Contact" Timeout issue | Max |  |  |  | 50000
|  | 16 | [2007-15] Check duplicate notification in Easy-Remit | Check duplicate notifications and reject them if duplicate notifications occur.
|  | 17 | [2007-Add03] - [MoneyGram] Review and update September release |  |  | Saroj
|  | 18 | [2008-Exim]-Transactions Automatically Route Request from Exim to Donga |  |  | Manoj
|  | 19 | [2009-01]-Sacom bank: Cash/Bank/Home delivery API |  |  | Saroj
|  | 20 | [2009-02]- Seperate Relationship list from Oversear Txn |  |  | Saroj
|  | 21 | [2009-04]-Seperate Real time API for GIBL Bank |  |  | Saroj
|  | 22 | [2009-06]-Real time service for IMEPay Wallet |  |  | Manoj
| Others | 23 | [2005-02] Limit amount on domestic txn | Domestic transaction and Withdraw should be failed from our side if customer try to send money more than KRW 6.5 Mil( Dont allowe Customer To send more than 6.5 Mil) | Max
|  | 24 | [2005-13] IME Cash Payment | Change Cash Payment Naming to Cash payment (IME)- Nepal Corridor Issue | Pralhad |  |  |  | 50000
|  | 25 | [2005-14] IME Wallet Payment | Change Mobile Wallet Naming to IME Pay Wallet- Nepal Corridor Issue | Pralhad |  |  |  | 50000
|  | 26 |  | The exchange rate calculation for Mongolia is slow for Contact-Mongolia Corridor | Pralhad |  |  |  | 50000
|  | 27 | [2007-Add01] Rocket Wallet Txn success but goto Agrani in New App
|  | 28 | [2007-Add02] - Customer Balance Mismatch and adjustment
|  | 29 | [2007-Add04] - Cannot move account Ledger
|  | 30 | [2007-Add05] - USD amt and Usd Rate not updated
|  | 31 | [2007-Add06] - New Compliance Rule for Nigeria
|  | 32 | Development for Missing Country flags
|  | 33 | Allow to edit State/district missing home delivery Txn
|  | 34 | [2008]-combine the inbound ledger for inbound and outbound
|  | 35 | [2008]-Change Calender for all accounting menus
|  | 36 | [2007] -KoronaPay : Status Update for Card Payment
|  | 37 | [2007]-Android Front Layout prepared same as iOS
|  | 38 | [Wing] Update Old duplicate control no
|  | 39 | Update missing country flags in website and Mobile App
|  | 40 | [2008]-Allow admin to modify the Temp transaction
|  | 41 | [2008]-Inbound Transaction from Payportal
|  | 42 | [2008-Error02]- MoneyGram: Put commit failed tarnsaction on Hold
|  | 43 | [2008]- MoneyGram : Send sender and receiver full name from API
|  | 45 | [2008-Thunes]- Allow fullname to send transaction
|  | 46 | [2008-MoneyGram]-Allow to send Optional name value/Add TT for API failed Txn
|  | 47 | [2008]- Report to check Failed Autodebit/wallet Txn
|  | 48 | [2008]-Auto stop scheduler for KBank INSUFFICIENT FUND transaction
|  | 49 | [2008-CommercialBank]-Valid Mobile format for SMS Notification to Receiver
|  | 50 | [2009-05]-Real time service for GME Nepal Bank Deposit
New Project | Online | 51 | [2005-19] Chinese translation in Online
| Core | 52 | [2005-11] Id visible in core system | Email id and user id both should be visible in Core system | Pralhad
|  | 53 | [2005-12] Primary-Secondary id visible in core system | Primary id card and secondary Id card both details Visible in Core system | Pralhad |  |  |  | 50000
|  | 54 |  | If Money Was deducted from customer Auto Debit and txn failed and money refunded to GME wallet , then there should be admin menu to check failed txn country wise | Pralhad | Ganesh |  |  | 50000
|  | 55 |  | Non KYC customer list Should be Editable | Pralhad | Ram |  |  | 50000
|  | 56 |  | Run status update sequence every 10 minutes for sri Lanka-Sri Lanka Corridor | Pralhad | Saroj |  |  | 50000
|  | 57 |  | Filter KFTC customer by customer user id and Expiry date | Pralhad |  |  |  | 50000
|  | 58 |  | Filter Customer by Id Expiry Date | Pralhad |  |  |  | 50000
|  | 59 |  | Admin Menu to hold realtime Txn | Pralhad |  |  |  | 500000
|  | 60 | [2008-16] Set Schedule for Push Notification | Set Schedule for Push Notification | Max |  |  | 2020-09-11 | 50000
|  | 61 | [2008-18] History for Push Notification | History for push notification | Max |  |  | 2020-09-11
|  | 62 | [2009-10] Image Push Notification | push notification with picture and links. | Max |  |  |  | 50000
|  | 63 |  | Location Based Push notification | Max |  |  |  | 50000
|  | 64 | 모바일앱을 다운로드했지만, 가입하지 않는 고객에 대한 Push | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | Max |  |  |  | 500000
|  | 65 |  | Block/Unblock Easy remit service by Admin User without needing IT support | Max |  |  |  | 50000
|  | 66 |  | Make it possible to send bulk emails from the system | Pralhad | Saroj/Ram |  |  | 50000
|  | 67 |  | Admin Menu to send Bulk SMS | Pralhad | Saroj/Ram |  |  | 50000
|  | 68 |  | All Branch Tellers to be able to login to different branch with single login ID | Pralhad | Manoj/Ganesh |  |  | 50000
|  | 69 |  | Capability to give country specific report according to native country of Admin user | Pralhad | Manoj/Ganesh |  |  | 500000
|  | 70 | [2006-04] Apply of return claim
|  | 71 | [2008-12] Report according to Native country
| Mobile | 72 | [2004-01] Reward Point-Coupon 2nd Phase | Reward Coupon 2nd Phase | Max | Max, JY |  | 2020-05-29 | 300000
|  | 73 | [2004-02] Allow Customer to Change Certain field | Allow Customers to Edit their Profile | Max | Max, JY |  | 2020-05-29 | 100000
|  | 74 | [2006-05] Simplifying the new registration | Simplifying the New Registration process by removing "Add auto Debit " and allow customer to login even without incomplete information | Subash |  |  |  | 500000
|  | 75 | [2005-03] Easy Remit with Korea-Seven | Easy Remit using LOTTE ATM | Max |  |  |  | 500000
|  | 76 |  | International Top-up from Tranglo | Pralhad |  |  |  | 100000
|  | 77 |  | Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | Pralhad |  |  |  | 50000
|  | 78 |  | Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Max | Andrew |  |  | 50000
|  | 79 |  | Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | Max | Andrew |  |  | 50000
|  | 80 | [2008-15] Transaction Details look up using KFTC API | Transaction Details lookup using KFTC API | Max |  |  | 2020-09-23 | 200000
|  | 81 | [2008-02] Downloadable in PDF File | Customer Statement downloadable in pdf from GME app | Max |  |  | 2020-09-23 | 100000
|  | 82 |  | Customers Contact mining and inviting Customers Contact to join GME App and send invitation or push message using kakaotalk | Max |  |  |  | 500000
|  | 83 |  | Online sim card Apply registration form in APP |  | Summer |  |  | 100000
|  | 84 | Deposit Money from Convenience Store | A service that allows you to deposit money from convenience store with Galaxia | Max |  |  |  | 200000
|  | 85 | Giftcon Service | Gifticon service using virtual account with Galaxia | Max
|  | 86 | Deposit Money from All ATMs | Service to deposit money from ATM | Max
|  | 87 | KJ Bank Firm banking Service | Service to virtual account using the firm banking of KJ-Bank | Max
|  | 88 | [2005-18] Chinese translation in Mobile App |  | Max | JB, Preyea | 2020-05-26 | 2020-06-04
|  | 89 | [2006-03] Verification of Country code for Flag
|  | 90 | [2007-18] Korea-Seven 2nd Phase | All customer can using Lotte ATM | Max |  |  | 2020-08-12
|  | 91 | [2008-01] Fixed bugs reported in Firebase Crashlytics |  | Max
|  | 92 | [2008-06] Domestic Txn for wallet to wallet | IT is transfer money from a wallet account to a wallet account | Max |  |  | 2020-08-20
|  | 93 | [2008-10] Notification on Mobile Update | The ability to notify customers when there is an important update, and the customer needs to update. | Max |  |  | 2020-09-23
|  | 94 | [2008-19] Collect of mobile phone contact | The ability to collect and store registered contacts on the customer's mobile phone in the DB.
|  | 95 | 핸드폰번호를 이용한 국내송금
|  | 96 | [2009-07] Adding Permission for Mobile App | Add location, storage, phone, address book, camera permissions
|  |  | [2009-08] Success message is printed when purchasing coupons | 거래내역조회를 할수 있는 쿠폰을 구매하는데 성공하면 출력하는 메시지를 변경
| API | 97 | [2008-21] TerraPay API | TerraPay API | Max
|  | 98 | [2008-20] DTOne API | International Top-up from DTOne | Max
|  | 99 | [2009-09] AliPay API | AliPay API | Max
|  | 100 | [2005-10] Exim bank | Exim Bank transaction have to make real time 24/7-Vietnam | Pralhad
|  | 101 |  | Uremit API | Pralhad |  |  |  | 100000
|  | 102 |  | NIUM API | Pralhad |  |  |  | 100000
|  | 103 | [2006-01] Card Payment API in Koronapay
|  | 104 | [2006-02] Direct Wallet Topup in IME Pay
|  | 105 | [2008-09] Bank Deposit for Singapore and Malaysia from Thunes | Bank Deposit for Singapore and Malaysia from Thunes
|  | 106 | [2006-10] Wing Realtime bank deposit API Integration | Wing Realtime Bank deposit API Integration | Pralhad | Saroj | Ongoing
|  | 107 | [2006-09] Card payment from Thunes | Starting Australia and Uzbekistan card payment from Thunes
|  | 108 | [2008-14] Realtime bank deposit from Kbank |  |  | Manoj | Ongoing
| Others | 109 |  | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | Max |  |  |  | 500000
|  | 110 |  | Fix the Zoho people issue with the server connection | Max |  |  |  | 50000
|  | 111 |  | New individual referral code for everyone | Max |  |  |  | 50000
|  | 112 |  | Online loan development together with online electronic Signature | Max |  |  |  | 500000
|  | 113 | [2005-16] Change G/W for KFTC | Change G/W for KFTC | Max | Max | 2020-05-01 | 2020-05-21
|  | 114 | [2008-11] Change Sender/Receiver Naming Rule on MoneyGram API | Change sender/receiver naming rule firstName = firstName + middleName(if not null) lastName = lastName1 + lastName2(if not null) |  |  |  | 2020-08-26
|  | 115 | 신용관리(계좌관리) 프로젝트
|  | 116 | [2007-19] Setup for In-house Banking System | In-house banking integration with Hana bank | Max |  |  |  | 300000
|  | 117 | [2005-17] 선불전자지급수단 발행및 관리업 라이선스 | E-PrePayment License | Max |  |  | 2020-08-21 | 500000
|  | 118 |  | AML and STR reporting system developing |  |  |  |  | 500000
|  | 119 |  | Develop the HR System for attendance, punctuality, annual leave, Payroll calculation |  |  |  |  | 2000000
|  | 120 |  | Bank of Korea Reporting through Fintech Association System API |  |  |  |  | 500000
|  | 121 |  | Integrate ERP with our System( GME Finance Crizen System) | Max |  |  |  | 300000
|  | 122 | [2007-11] GME System Consulting | GME System Consulting | Max
|  | 123 | [2007-10] Setup SVN in Korea | Setup SVN in Korea | Max
|  | 124 | [2007-04] Sepatate IIS Server | Separating WEB with WEB and WAS | Max |  |  | 2020-08-05
|  | 125 | [2006-14] DB Encryption | DB Encryption using Symmetric Key(AES-256) | Max |  |  | 2020-08-05
|  | 126 | [2009-01] System Monitoring and Send SMS | It is the ability to send a warning message when something unusual occurs during system surveillance. | Max
|  | 127 | [2007-13] Manual for Admin Page
|  | 128 | [2007-14] Open-Banking API | Change of API parameters for open banking-withdraw |  |  |  | 2020-07-31
|  | 129 | [2008-17] Mobile App Tracking on Firebase | Mobile App Tracking on Firebase
|  | 130 |  | GME Pay solution enhancing and doing API with local partners | Max |  |  |  | 1000000
|  | 131 | [2006-15] GME Pay App | GME Pay App | Max |  |  | 2020-08-05
|  | 132 | [2009-02] Other development | 1) 포인트 상품 리스트에서 스피커를 삭제 2) 해외/국내 송금 영수증 화면에 송금시간을 추가 3) 해외/국내 송금 영수증 화면에 보낸사람이름을 추가 4) 국내송금에서 송금받는 계좌번호를 숫자로만 입력(iOS)
| System/Infra | 132 | [2005-15] Security inspection of GME |  | Max
|  | 133 | [2006-13] GME System Upgrade Plan | GME System Upgrade Plan | Max
|  | 134 | [2007-02] DB Redundancy | DB Redundancy | Max
|  | 135 | [2007-03] DB Access Control | DB Access Control | Max
|  | 136 | [2007-05] Setup Firewall | Firewall Setup at HQ | Max |  |  | 2020-08-05
|  | 137 | [2007-06] Setup NAC | NAC Setup at HQ | Max |  |  | 2020-08-05
|  | 138 | [2007-07] Setup Vaccine | Vaccine Setup at HQ | Max |  |  | 2020-08-05
|  | 139 | [2007-08] Setup IPSEC VPN | IPSEC VPN Setup at HQ and FSDC | Max |  |  | 2020-08-05
|  | 140 | [2007-09] Setup VPN Redundancy | Operational VPN Redundancy Setup | Max
|  | 141 | [2007-16] Setup NTP |  |  |  |  | 2020-08-05
|  | 142 | [2008-05] 금융보안원 기업보안점검
|  | 143 | [2008-F01] DB Migration | DB Migration
|  | 144 | [2008-F02] 이용기관점검 from 금융보안원
|  | 145 | [2009-F01] Setup FTP in DB
|  | 146 | [2009-F02] E-Prepayment License 리스트 작성
| Supplement | 147 | [2008-E01] Change Fingerprint Logic | Fingerprint error in last step of transaction, even after put the correct password, message will say OTP IS WRONG |  |  |  | 2020-08-19
|  | 148 | [2008-E02] ChannelTalk SDK Update | 채널톡에서 SDK를 업데이트해서, 이미지가 안보이는 현상을 보완 |  |  |  | 2020-08-19
|  |  |  | Total |  |  |  |  | 5700000
Auto remit with Korea-Seven

## 2020-Q4
Group | Category | SN | 우선순위 | Project Code (Name) | Description | 설명 | PIC | Developer | Start Date | End Date | Incentive | Incentive
Issue | Online
| Core | 1 | 3 |  | The core system menu is Slow/doesn’t show: System Security>user logs and Admin>Customer Mangement> Customer statement>Transaction statemetn |  |  |  |  | 2020-12-10 | 50000 | 50000
|  |  |  | [2010-04] City field | The city field is shown by the city name.
| Mobile | 2 | 52 |  | Update missing country flags in website and Mobile App |  |  |  |  | 2020-12-10 | 50000 | 50000
|  | 3 | 38 | [2007-15] Check duplicate notification in Easy-Remit | Check duplicate notifications and reject them if duplicate notifications occur. |  |  |  |  | 2021-01-15 | 200000 | 200000
|  | 4 | 49 | [2009-01]-Sacom bank: Cash/Bank/Home delivery API |  |  |  | Saroj |  | 2020-11-01 | 100000 | 200000
|  | 5 | 50 | [2009-02]- Seperate Relationship list from Oversear Txn |  |  |  | Saroj |  |  | 50000 | 50000
| Others | 6 | 21 |  | Correct some Thai sentences at Lotte ATM - file sent to Pagna by kakao-talk | 롯데 ATM에서 태국언어에 대한 오류 |  |  |  | 2021-01-30 | 50000 | 50000
|  |  |  | [2011-03] ID Card display |  |  |  | Kyle |  | 2020-11-16
New Project | Online |  |  | [2010-02] GME Pay Terms and Conditions | GME Pay Term and Condition (Web and App) | GME Pay 이용약관 (Web, App)
|  |  |  | [2010-03] MultiLanguage for Arab and French |  | 아랍과 프랑스 언어
|  |  |  | [2010-08] Meta tag update in Online | Meta tag update in Online | GME웹페이지에서 Meta Tag를 업데이트한다
| Core | 7 | 4 | [2012-06] Modify Receiver Information in Recepit Page | Send modification requests from customer to the corridor admin users. When requesting for modification allow customer to chose what to modify and what is the new value to modify to | 송금영수증 페이지에서 수신자정보를 변경해서 다시 송금할 수 있도록 하는 기능 |  |  |  |  | 50000 | 100000
|  | 8 | 7 | [2012-07] Add native country filter in Non KYC list | Add native country filter in Non kyc list. | Administrator - Non KYC User메뉴에서 [Native Country] 필드를 추가해서 조회가능한 기능 |  | Manoj |  | 2020-12-01 | 50000 | 50000
|  | 9 | 12 | [2010-05] Send Transaction Status once paid to sender as a push notification | send transaction status once paid to sender as a push notification | 송금상태가 'PAID"이면, 송금인에게 Push 메시지를 전송하는 기능 |  | Manoj |  |  | 50000 | 50000
|  | 10 | 13 | [2012-09] Search the Domestic Txn by GME Control No | Search the Domestic transaction by GME Control No. just like international Txn | 국내송금에서 GME Control No를 가지고 조회할 수 있는 기능 |  | Manoj |  | 2020-12-31 | 50000 | 50000
|  | 11 | 15 | [2012-10] Send SMS notification to Sender after Domestic Txn is Successful | Send SMS notification to Sender after Domestic Transfer is successful | 국내송금이 성공하면 보낸사람에게 SMS로 성공메시지를 전송하는 기능 |  | Manoj |  | 2020-12-31 | 50000 | 50000
|  | 12 | 24 | [2012-13] Filter Auto Debit by Native Country and Expiry Date | Filter Auto debit by native country and expiry date | ?? |  | Manoj |  | 2020-12-31 | 50000 | 50000
|  | 13 | 26 | [2012-14] Admin Menu to Hold RealTime Txn | Admin Menu to hold realtime Txn |  |  | Saroj Manoj |  |  | 500000 | 300000
|  | 14 | 29 | [2009-10] Image Push Notification | push notification with picture and links. |  | Max |  |  |  | 50000 | 50000
|  | 15 | 30 |  | Location Based Push notification | 위치정보에 따른 Push Notification | Max |  |  |  | 50000 | 100000
|  | 16 | 34 |  | New individual referral code for everyone | [5 empty] | 50000 | 50000
|  | 17 | 67 | [2012-16] Admin Page for KJ Bank Deposit Error | Admin Page for KJ Bank deposit error | 광주은행 입금실패에 대한 원인을 제공하는 페이지 제공 |  | Manoj |  |  | 50000 | 50000
|  | 18 | 37 | [2006-04] Apply of return claim | [6 empty] | 100000 | 100000
|  | 19 | 25 |  | Inbound Fx Calculation | [5 empty] | 50000 | 50000
|  | 20 |  | 모바일앱을 다운로드했지만, 가입하지 않는 고객에 대한 Push | Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages |  | Max
|  |  |  | [2011-06] Validation required during customer registration process | 온라인과 관리자페이지에서 회원가입시 1) 국적을 한국으로 선택하면, 주민등록증만 선택 2) 국적을 외국으로 선택하면, 여권과 외국인등록증을 선택 |  |  |  |  | 2020-11-01
|  |  |  | [2011-08] Cancel cash-pickup in Cebuana |  | 우리는 세부아나 현금 픽업 거래를 수정하고 취소해야 하는 문제가 있는데, 아래 메뉴를 통해 우리 쪽에서 취소 및 수정 거래를 할 수 있도록 해주길 바란다. • Gme Core System에서 수정/직접 요청 전송 • Gme Core 시스템에서 요청 취소/직접 |  |  |  | 2021-01-15
|  |  |  | [2012-18] Reason field in Coupon Issuance |  | 쿠폰을 발행할때, 쿠폰발행에 대한 이유를 기록할 수 있는 필드를 추가한다.
|  |  |  | [2012-19] Check Referral Report |  | Register Report와 Transaction Report가 이상한 부분에 데한 체크
|  |  |  | [2012-21] Add Bank Account No in OFAC Management |  | OFAC Mananement에서 은행계좌필드를 추가 |  |  |  | 2021-01-15
| Mobile | 21 | 1 | [2012-04] Add "Receiving Bank" in Confirm Page | While sending money at the confirmation page add "Receiving Bank Name" | 송금확인 페이지에서 수신받는 은행을 표시 |  | Manoj Andrew Dibya |  | 2020-12-31 | 50000 | 50000
|  | 22 | 2 | [2012-05] Translation for Bank Names in native language with bank logo | Translation for Bank Names in native language with bank logo | 은행이름의 다국어표현과 은행 로고를 추가 |  | Saroj Andrew Dibya |  |  | 50000 | 100000
|  | 23 | 5 |  | make it possible to delete notices in notice board of customers app (all the customers once and one by one too) | Notice, Notification 에 대한 고객의 삭제기능 추가 |  |  |  |  | 50000 | 100000
|  | 24 | 6 |  | Show exact time and sender name in transaction report (Customer side) | 송금 영수증 페이지에서 송금시간과 송금인의 이름을 보여주는 기능 |  |  |  |  | 50000 | 50000
|  | 25 | 11 | [2012-08] Add remark field in Domestic Txn | Make it possible to add a Remarks while doing Domestic Transfer so that receiver can see the remark in his statement | 국내이체에서 받는통장메모 기능을 추가 |  | Summer |  |  | 50000 | 50000
|  | 26 | 31 |  | Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Notice, Notification을 분리하는 기능 | Max | Andrew |  |  | 50000 | 50000
|  | 27 | 32 |  | Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | Notice는 로그인할때마다 팝업으로 표시 알림은 하루 최대 2회만 팝업 | Max | Andrew |  |  | 50000 | 50000
|  | 28 | 16 | [2012-11] Upload New Photo in Admin Page | include a button in Admin System to request to upload new photos. then we don't need to request photos but request them to upload | ID Card를 업로드하는 기능 - 관리자페이지? 모바일앱? |  | Manoj |  |  | 100000 | 100000
|  | 29 | 17 |  | Make it possible to see customers basic info including bank A/C and their ID Photos (small preview) from the app | 고객의 계좌번호와 ID Card를 확인하는 기능 계좌번호 변경과 ID Card를 변경하는 기능 |  |  |  |  | 100000 | 100000
|  | 30 | 33 |  | Customers Contact mining and inviting Customers Contact to join GME App and send invitation or push message using kakaotalk |  | Max |  |  |  | 500000 | 500000
|  | 31 | 35 |  | Online sim card Apply registration form in APP Make it possible to apply for a sim card using GME Remit app | GME 앱을 이용해 SIM 카드를 신청 |  | Summer |  |  | 100000 | 100000
|  | 32 | 53 | [2011-02] Deposit Money from Convenience Store | A service that allows you to deposit money from convenience store with Galaxia | 편의점에서 가상계좌 입금 | Max |  |  | 2020-12-15 | 500000 | 500000
|  | 33 | 55 | [2011-04] Giftcon Service | Gifticon service using virtual account with Galaxia | 기프트콘 서비스 | Max |  |  |  | 500000 | 700000
|  | 34 | 19 | [2010-01] KJ Bank Firm banking Service | Service to virtual account using the firm banking of KJ-Bank Develop local transfer to be able to payment coupang/G-market online shopping account | KFTC 오픈뱅킹 서비스에서 수신자명 조회 스킵하는 방식으로 처리 | Max |  |  | 2020.10.23 | 200000 | 200000
|  | 35 | 18 |  | make it possible to find the branch location using a map site(google, naver and Kakao) from the app. currently we have only addresses | 지도앱(구글,네이버,카카오)을 이용해서 지점을 찾을수 있는 기능 |  |  |  | 2021-01-20 | 50000 | 50000
|  | 36 | 20 | [2012-12] Show service charge 0 | Show service charge 0 in the transaction report for used coupon transaction | 쿠폰을 사용해서 송금한 경우에, 영수증에 서비스요금이 0으로 표시 |  | Manoj |  | 2020-12-31 | 100000 | 50000
|  | 37 | 22 |  | Describe Lotte ATM withdraw fee on App | 앱에 롯데ATM에서 출금하는 경우에 서비스요금에 대한 설명 |  |  |  |  | 50000 | 50000
|  | 38 | 54 | [2008-01] Fixed bugs reported in Firebase Crashlytics |  |  | Max |  |  |  | 50000 | 100000
|  | 39 | 28 |  | Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | 새로운 알림(Notification)에 대한 벨아이콘 표시 |  |  |  |  | 50000 | 50000
|  | 40 | 36 |  | Online loan development together with online electronic Signature | [5 empty] | 500000 | 500000
|  | 41 |  | Deposit Money from All ATMs | Service to deposit money from ATM | 모든 ATM기기에서 입금이 가능한 기능 | Max
|  | 42 | 68 | [2008-19] Collect of mobile phone contact | The ability to collect and store registered contacts on the customer's mobile phone in the DB. | 모바일폰 주소록 수집
|  | 43 |  | 핸드폰번호를 이용한 국내송금
|  | 44 | 69 | [2009-07] Adding Permission for Mobile App | Add location, storage, phone, address book, camera permissions
|  | 45 |  | [2009-08] Success message is printed when purchasing coupons | 거래내역조회를 할수 있는 쿠폰을 구매하는데 성공하면 출력하는 메시지를 변경
[5 empty] | 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다. | 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다.
|  |  |  | [2010-03] MultiLanguage for Arab and French |  | 아랍과 프랑스 언어
송금완료페이지 혹은 송금실행 직전에 현지까지 송금되는 시간을 미리 공지 연휴기간(춘절,중추절)내 송금 지연 시간 사전 고지
에러메시지 내용의 효율성 - 해당현상이 반복되는 경우 고객센터로 문의해 주세요. - 전화문의, 카카오톡
|  |  |  | [2010-06] Timeout Processing in Mobile App | Timeout Processing - If the server has not responded for 30 seconds, time out processing (go to the previous page) | [모바일앱] Timeout처리 - 서버에서 30초간 응답이 없는 경우, 타임아웃처리(이전페이지로 이동)
|  |  |  | [2010-07] Navigation Bar Complementation in Android | Android-Bottom Navigation Bar Complementation | [안드로이드] 하단 네비게이션 보완
|  |  |  | [2011-10] Relogin when re-running the app | 안드로이드앱을 다시 실행시키면, 로그인을 다시 물어보는 기능을 추가 |  |  |  |  | 2020-12-15
|  |  |  | [2012-01] Java Exception Error | 회원가입후에 최초 실행시에 Java Exception Error 발생에 대한 이슈 |  |  | Preyea | 2020-12-07
|  |  |  | [2012-17] Change Transaction ID to GME Control No | Change Transaction ID to GME Control No in Receipt PDF | PDF영수증 페이지에서 Transaction ID를 GME Control No로 변경 |  | Manoj Preyea Dibya |  | 2020-12-31
| API |  |  | KFTC OpenBanking API | KFTC Open Banking API의 API라이브러리화
|  |  |  | [2011-05] Openbanking API v2.3 Update | 오픈뱅킹 API 버전 2.3 으로 업데이트 |  |  | JY |  | 2020-12-15
|  | 46 | 9 | [2008-21] TerraPay API | TerraPay API |  | Max |  |  |  | 100000 | 200000
|  | 47 | 27 | [2008-20] DTOne API | International Top-up from DTOne |  | Max | JY |  | 2020-11-01 | 100000 | 200000
|  | 48 | 63 |  | BRAC Back API | [5 empty] | 100000 | 200000
|  | 49 | 65 | [2009-09] AliPay API | AliPay API |  | Max |  |  | 2021-01-15 | 100000 | 200000
|  | 51 |  |  | Uremit API |  | Pralhad
|  | 52 |  |  | NIUM API |  | Pralhad
|  | 53 | 8 |  | IME London API | [5 empty] | 100000 | 200000
|  | 54 | 10 |  | Sigue API | [5 empty] | 100000 | 200000
|  | 55 | 23 |  | Bill Payment in Indonesia- API | [5 empty] | 100000 | 100000
|  | 56 | 66 | [2011-01] Auto Remit with Korea-Seven | Auto Remit with Korea Seven | [5 empty] | 200000 | 300000
|  | 57 | 14 |  | Develop SMS function using kakaotalk notification | SMS 전송을 카카오 알림톡으로 교체 |  |  |  |  | 100000 | 300000
|  | 58 | 51 | [2007-Add01] Rocket Wallet Txn success but goto Agrani in New App | [2007-Add01] Rocket Wallet Txn success but goto Agrani in New App |  |  |  |  | 2020-12-15 | 50000 | 50000
|  | 59 |  | 신용관리(계좌관리) 프로젝트
|  | 60 | 39 |  | AML and STR reporting system developing | [5 empty] | 500000 | 500000
|  | 61 | 40 |  | Develop the HR System for attendance, punctuality, annual leave, Payroll calculation | [5 empty] | 2000000 | 2000000
|  | 62 | 41 |  | Bank of Korea Reporting through Fintech Association System API | [5 empty] | 500000 | 500000
|  | 63 | 42 |  | Integrate ERP with our System( GME Finance Crizen System) |  | Max |  |  |  | 300000 | 300000
|  | 64 | 47 | [2007-11] GME System Consulting | GME System Consulting |  | Max |  |  |  | 300000 | 500000
|  | 65 | 46 | [2007-10] Setup GitLab and SVN in Korea | Setup GitLab and SVN in Korea |  | Max |  |  |  | 200000 | 200000
|  | 66 | 48 | [2009-01] System Monitoring and Send SMS | It is the ability to send a warning message when something unusual occurs during system surveillance. Automatic SMS sending when the system is at risk |  | Max | Kyle |  | 2020.10.23 | 100000 | 100000
|  | 67 |  | [2008-17] Mobile App Tracking on Firebase | Mobile App Tracking on Firebase
|  | 68 | 43 |  | GME Pay solution enhancing and doing API with local partners |  | Max
|  | 69 | 56 | [2012-15] Support to receive inbound | Support to receive inbound from partner through pull method like E9Pay |  |  | Manoj |  |  | 200000 | 200000
|  | 70 | 57 |  | Add Commercial Bank transactions to "transaction manual reprocess" menu | [5 empty] | 50000 | 50000
|  | 71 | 58 |  | Notification popup after login [to support marketing part] | [5 empty] | 50000 | 50000
|  | 72 | 59 |  | Schedule Bulk push notification/ Personal notification with "Name" | [5 empty] | 50000 | 50000
|  | 73 | 61 |  | Make API with People's bank once we sign the agreement | [5 empty] | 100000 | 100000
|  | 74 | 62 | [2012-16] Show the business days on App | Show the business days on App (CB/KBZ - real time, Others - 3~5 days) for Myanmar Only |  |  | Manoj |  |  | 100000 | 100000
|  | 75 | 64 |  | Route Txn based on Amount | [5 empty] | 1000000 | 1000000
|  |  |  | [2011-07] Supplement of KFTC and KJ Duplicate Transactions |  | 오픈뱅킹을 이용해서 입금이체를 시도하는 중에 결과확인에 대한 결과를 받으면, 광주은행 API를 이용해서 입금이체를 시도하지 않아야 한다.(이중지불문제)
|  |  |  | [2011-09] EP Corridor API(AliPay) |  |  |  | Kyle
|  |  |  | [2012-20] Korona Pay Status Synchronize |  | 1) 코로나페이는 일부 거래에 대해서 Cancel로 상태를 변경하지만, GME는 수동으로 요청할때까지 "Payment"상태를 유지한다. 2) 코로나페이는 거래후 1분동안 결제상태를 업데이트 하지만, GME는 30분정도 결제상태를 유지한다. |  |  |  | 2020-12-15
| Other |  |  | [2012-02] Setup Facebook Pixel | [5 empty] | 2020-12-15
|  |  |  | [2012-03] Send Second SMS to customer who do txn from MoneyGram | [5 empty] | 2020-12-15
| Infra | 77 | 44 | [2006-13] GME System Upgrade Plan | GME System Upgrade Plan |  | Max |  |  |  | 50000 | 100000
|  | 78 | 45 | [2007-02] DB Redundancy | DB Redundancy |  | Max |  |  |  | 300000 | 300000
|  | 79 |  | [2007-09] Setup VPN Redundancy | Operational VPN Redundancy Setup |  | Max
|  | 80 |  | [2010-05] 이용기관점검 | 이용기관점검(금융보안원) : 부분이행항목에 대한 점검 |  | Max |  |  | 2020-10-27
Total
[11 empty] | 11650000 | 13100000

## 2021-Q1
2021년 1분기 프로젝트
Project Code(Name) | Description | 설명 | Core | Online | Server/API | Mobile | Other | Infra | 시작일 | 목표일 | 종료일 | 배포일
[2007-10] Setup GitLab and SVN in Korea | Setup GitLab and SVN in Korea | [5 empty] | Kyle
[2009-02] Seperate Relationship list from Oversear Txn | [2009-02]- Seperate Relationship list from Overseas Txn |  | O
[2011-01] Auto Remit with Korea-Seven | Auto Remit with Korea Seven |  | JY |  | JY |  |  |  | 2021-01-18 | 2021-01-20
[2011-04] Giftcon Service | Gifticon service using virtual account with Galaxia | 기프트콘 서비스 | JY |  | JY | A,D |  |  | 2021-01-28 | 2021-02-17 | 2021-02-24 | 2021-02-25
[2012-05] Translation for Bank Names in native language with bank logo | Translation for Bank Names in native language with bank logo | 은행로고가 있는 다국어로 은행을 표시 | Saroj |  | Saroj | Preyea Dibya |  |  | 2021-02-08 | 2021-02-26
[2012-08] Add remark field in Domestic Txn | Make it possible to add a Remarks while doing Domestic Transfer so that receiver can see the remark in his statement | 입금계좌 인자내역을 추가하는 기능 |  |  | Kyle | Andrew Dibya |  |  | 2021-01-25 | 2021-01-29 |  | 2021-02-22
[2012-11] Upload New Photo in Admin Page | include a button in Admin System to request to upload new photos. then we don't need to request photos but request them to upload | ID Card.를 업로드하는 기능 | O |  | O | O |  |  |  |  | Preyea가 개발완료 iOS 아직 개발미진행
[2012-14] Admin Menu to Hold RealTime Txn | Admin Menu to hold realtime Txn |  | O |  | O
[2012-16] Admin Page for KJ Bank Deposit Error | Admin Page for KJ Bank Deposit error | 광주은행 입금실패에 대한 원인을 제공하는 관리자 페이지 | Kyle |  | Kyle |  |  |  | 2021-01-25 | 2021-01-29
[2012-18] Reason field in Coupon Issuance |  | 쿠폰을 발행할때, 쿠폰발행에 대한 이유를 기록할 수 있는 필드를 추가한다. | JY | [5 empty] | 2021-01-14 | 2021-01-27 |  | 2021-02-24
[2012-19] Check Referral Report |  | Register Report와 Transaction Report가 이상한 부분에 대한 체크 | Summer | [5 empty] | 2021-02-01 | 2021-02-10 |  | 2021-02-24
[2101-01] Manual for Overseas Remittance Voucher | Creating an account subject for overseas remittances and preparing a manual on how to generate a statement for each partner 1) How to create an account subject 2) How to link accounts with overseas remittances 3) How to add a statement after the overseas remittance is completed 4) How to add a statement after an overseas remittance is canceled | 해외송금에 대한 계정과목 생성 및 파트너별로 전표를 생성하는 방법에 대한 매뉴얼 작성 1) 계정과목 생성방법 2) 해외송금에서 계정과목을 연동하는 방법 3) 해외송금이 완료된 이후에 전표를 추가하는 방법 4) 해외송금이 취소된 이후에 전표를 추가하는 방법 |  |  |  |  | O
[2101-02] Link in Map | Add links to branch addresses using maps (Naver, Google, Kakao) | 지점의 주소를 지도(네이버,구글,카카오)를 이용해서 링크를 추가 |  |  |  | A, D |  |  | 2021-01-14 | 2021-01-20 | 2021-01-28 | 2021-02-25(A)
[2101-03] MultiLanguage of Permission Commnet |  | 권한 설명의 다국어버전 |  |  |  | A, D |  |  | 2021-01-21 | 2021-01-22 | 2021-02-08(개발) | 2021-02-25(A)
[2101-04] ProgressBar in Edit Recipient | Adding a progress bar when loading the Edit Recipient | Edit Recipient 페이지 로딩시 프로그래스바 추가 |  |  |  | A, D |  |  | 2021-01-15 | 2021-01-20 | 2021-01-28(개발) | 2021-01-28
[2101-05] Add Sender Country(South Korea) in Receipt PDF |  | PDF 영수증에서 송금국가(South Korea) 추가 |  |  |  | A, D |  |  | 2021-01-21 | 2021-01-22 | 2021-01-25(개발) | 2021-02-25(A)
[2101-06] Smart Deposit in Admin |  |  | Summer | [5 empty] | 2101-01-15 | 2101-01-29 | 2101-02-08(개발) | 2021-02-24
[2101-07] GME Pay in Admin |  |  | Summer | [5 empty] | 2101-02-10 | 2101-02-18 |  | 2021-02-24
[2101-08] SIGUE Inbound API | SIGUE Inbound API |  | Saroj |  | Manoj Ram |  |  |  | 2021-01-18 | 2021-02-10
[2101-23] KoronaPay Inbound API |  |  | Saroj |  | Anil Ram | Preyea Dibya |  |  |  | 2021-01-25
[2102-11] Core logic for Inbound API | Dynamic API Routing and Core Inbound Functionality | [5 empty] | Saroj |  | 2021-02-10 | 2021-02-25
[2102-06] Inbound Transaction pay API Endpoints | Features that can be checked on the Mobile App when an Inbound remittance is received | Inbound송금이 들어오면, Mobile App에서 확인이 가능한 기능 |  |  | Saroj | Preyea Dibya | Saroj |  |  |  | Android: Done iOS: on going
[2103-28] Check Real Name in Inbound Account |  | 1) 인바운드 계좌 등록에서 실명조회를 하는 기능을 추가
[2101-09] Change Upload Location for ID Card Image |  | 신분증 이미지 업로드 패스 변경 | Kyle | Kyle | Kyle |  |  |  | 2021-01-18 | 2021-01-29 | 2021-01-29(개발)
[2101-10] Supplement of KFTC and KJ Duplicate Transactions |  | 오픈뱅킹을 이용해서 입금이체를 시도하는 중에 결과확인에 대한 결과를 받으면, 광주은행 API를 이용해서 입금이체를 시도하지 않아야 한다.(이중지불문제) |  |  | Kyle |  |  |  | 2021-01-25 | 2021-01-27 | 2021-01-26 | 2021-01-26
[2101-11] DB Migration | [6 empty] | Max,Dana |  | 2021-01-25 | 2021-01-26 | 2021-01-26 | 2021-01-26
[2101-12] Add for Apply loan in GME Finance |  | GME 대부 홈페이지에서 론을 신청하는 페이지를 추가 |  |  |  |  | Summer |  | 2021-01-21 | 2021-01-26 | 2021-01-29
[2101-13] Change the Minimum Amount of Domestic Remittance to 100KRW |  | 국내송금에서 최소 송금금액을 100원으로 변경 |  |  | JY | A, D |  |  | 2021-01-21 | 2021-01-22 | 2021-01-22 | 2021-01-22
[2101-14] Automatic Name Check from Admin |  | 관리자페이지에서 실지명의조회를 외국인등록번호와 여권을 이용해서 자동으로 체크할 수 있도록 하는 기능 | Summer |  | Summer |  |  |  | 2021-01-25 | 2021-01-27 |  | 2021-02-24
[2101-15] GME Homepage Renewal |  |  |  | Kyle |  |  |  |  | 2021-02-01 | 2021-02-05 | 2021-02-08 | 2021-02-22
[2101-16] Transaction Status Change in Admin | Transtatus, Paystatus changed by Operation team |  | Manoj | [6 empty] | 2021-01-20 | 2021-01-20 | 2021-01-20
[2101-17] Delete auto-debit account in Admin |  |  | Manoj | [6 empty] | 2021-01-15 | 2021-01-15 | 2021-01-15
[2101-18] TerraPay API | TerraPay API |  | Manoj |  | O |  |  |  | 2021-02-01 | 2021-02-05
[2101-19] People's Bank API | People's Bank API |  | Manoj |  | O | [6 empty] | 2021-02-19
[2101-20] Unable to modify customer information | Customers shall not be able to modify their personal information after the completion of membership registration. | 고객은 회원가입완료 이후에는 개인정보를 수정할 수 없어야 한다. 현재 회원가입하고, 1원송금이 완료되지 않은 상태에서 뒤로가기 버튼등으로 회원정보수정이 가능하다 |  |  |  | Preyea Dibya |  |  | 2021-02-03 | 2021-02-04
[2101-21] Change default value 100,000KRW in Mobile Wallet |  | Mobile Wallet서비스에서 Send Money를 100,000원으로 디폴트 지정한다. |  |  | O | O | [5 empty] | A: 2021-02-25
[2101-24] MoneyGram API | Catalog download (Service, Bank, Payment Method, etc) |  |  |  | Saroj |  |  |  |  | 2021-01-26 | 2021-01-26 | 2021-01-26
[2101-25] Branch agent update for all bangladesh partner (Dutch Bangla, Islami, Agrani) | Bangladesh Third bank brach update in GME system | [5 empty] | Manoj |  | 2021-01-27 | 2021-02-01 | 2021-02-08 | 2021-02-08
[2101-26] Add Memo field in Customer Profile |  |  | Manoj | [5 empty] | 2021-01-29 | 2021-02-05 | 2021-02-09
[2101-27] Add Agent for Pakistan from MoneyGram | [6 empty] | Manoj |  | 2021-01-27 | 2021-01-29 | 2021-02-02 | 2021-02-02
[2101-28] Upload Customer Document from Core System | Provide an administrator page where you can request the customer's ID Card image again. Employees re-request ID Card images from the Admin page to the customer The customer checks the ID Card image request in the app and uploads the ID Card image. | 고객의 ID Card이미지를 다시 요청할 수 있는 관리자페이지 제공 직원은 관리자페이지에서 고객에게 ID Card이미지를 다시 요청 고객은 앱에 팝업으로 ID Card이미지 요청을 확인하고, ID Card이미지를 업로드한다. | Manoj |  | Manoj | Preyea Dibya |  |  | 2021-01-15 | 2021-02-04 | Android: Done iOS: not start
[2101-29] Check out $50,000 per year in Compliance |  |  | Manoj |  |  |  | Manoj |  | 2021-01-10 | 2021-02-10 | 2021-02-10 | 2021-02-09
[2101-30] Setup Commission Fee in Leger from MoneyGram | [6 empty] | Manoj |  | 2021-01-28 | 2021-02-02 | 2021-02-02 | 2101-02-02
[2101-31] Fix in Transaction & Registration Menu |  | Remittance > Reports > Transaction & Registration Menu 이슈에 대한 해결 |  |  |  |  | Manoj |  | 2021-01-18 | 2021-01-22 | 2021-01-22 | 2021-01-22
[2101-32] RIA API (new) |  | 기존의 ThirdParty API 에서 신규 API개발 |  |  |  |  | Saroj Ram |  | 2021-01-11 | 2021-01-28 | 2021-01-28 | 2021-01-28
[2101-33] Trouble Ticket from SacomBank |  | Sacom Bank API에서 Trouble Ticket 추가 |  |  |  |  | Saroj Ram |  | 2021-01-20 | 2021-01-28 | 2021-01-28
[2101-34] Agrani Bank API | [6 empty] | Saroj |  | 2021-01-22 | 2021-02-05 | 2021-02-05
[2101-35] USD Currency in Vietenam | [8 empty] | 2021-02-01 | 2021-02-02 | 2021-02-02 | 2021-02-02
[2102-01] Change Default Currency in Africa | Change Today's Rate's You Send to 100,000 won in African countries (Kenya, Ghana, Uganda, Rwanda, Zambia) | 아프리카국가(Kenya, Ghana, Uganda, Rwanda, Zambia)에서 Today's Rate 의 You Send를 100,000원으로 변경 |  |  | Saroj | Andrew Dibya |  |  | 2021-02-15 | 2021-02-15
[2102-02] Change Date Format in Mobile App | Unify date format in mobile apps (MMM d yyyy h:mm a) ex)Jan 29 2021 10:19 AM | 모바일앱에서 날짜표기형식을 통일 (MMM d yyyy h:mm a) ex)Jan 29 2021 10:19 AM |  |  | Summer | Andrew |  |  | 2021-02-04 | 2021-02-26
[2102-03] Analysis in Admin Page - Account Statement |  | Account Statement 메뉴가 속도가 느린 이유에 대한 원인 분석 | Saroj | [5 empty] | 2021-02-05 | 2021-02-10
[2102-04] Analysis in Admin Page - Treasury Deal Booking |  | Treasury Deal Booking 메뉴가 속도가 느린 이유에 대한 원인 분석 | Manoj | [5 empty] | 2021-02-05 | 2021-02-10
[2102-05] Apply of Return Claim | Apply of Return Claim | 거래완료된 입금이체에 대해서 자금반환을 청구하는 관리자페이지 | Kyle | [5 empty] | 2021-02-09 | 2021-02-16
[2102-07] Remittance of South African currency
[2102-08] Separating for Notice and Notification |  | 1. 현재 Notice 의 기능을 Notice 와 Notification 으로 분리해서 운영 2. Notice는 삭제되지 않고, Notification은 고객의 요청에 의해서 삭제할 수 있다. 3. 새로운 Notice에 대해서 벨아이콘으로 표시하는 기능 4. Notice와 Notification은 날짜에 의해서 정렬이 가능하도록 5. Notice와 Notification은 제목과 내용에 의해서 검색이 가능하도록 6. 새로운 Notice는 고객이 로그인할때, 하루에 2번 팝업으로 안내할 수 있는 기능 7. 영업직원이 Notification 팝업메시지를 전송할 수 있는 기능
[2102-09] Show Up Service Fee for Withdraw Service | Describe Lotte ATM withdraw fee on App | 모바일앱에서 출금수수료에 대한 안내 |  |  |  | Andrew Dibya
[2102-10] Guide screen for Smart Deposit service | Guide screen for Smart Deposit service | Smart Deposit 서비스에 대한 가이드 화면(Gmoney) |  |  |  | Andrew Dibya
[2102-12] Notice Page for System Check(Failure) |  | 시스템 점검 및 장애에 대한 공지페이지 제작 |  |  |  | Andrew Dibya |  |  | 2021-02-17 | 2021-02-19 |  | A: 2021-02-24
[2102-13] Specify the Order for Remittance Methods | Switch order of Cash Payment, Bank Deposit, Mobile Wallet appearing in mobile app flexibly | 모바일 앱에 나타나는 현금결제, 은행예금, 모바일 지갑의 전환 순서 |  |  |  | Saroj |  |  | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19
[2102-14] Complementing Myanmar language in mobile apps |  | 모바일 앱에서 미얀마 언어에 대한 보완 |  |  | Kyle | Andrew Dibya |  |  | 2021-02-22 | 2021-02-23 |  | A: 2021-03-02
[2102-15] KFTC FinTech Information Provider API |  | 오픈뱅킹 핀테크업 정보제공자 API |  |  | Kyle |  |  |  | 2021-02-24 | 2021-03-12
[2102-16] Copy and Paste Wallet Account Number in Mobile App |  | 모바일앱에서 가상계좌번호를 복사하는 기능 |  |  |  | Andrew Dibya |  |  | 2021-02-23 | 2021-02-23
[2102-17] Renewal for GME Finance Homepage | [6 empty] | Summer |  | 2021-02-26 | 2021-03-02 | 2021-03-02 | 2021-03-02
[2103-01] Archive Old Accounting DB | Archive 2017, 2018 and 2019 Accounting DB to separate DB | 2017,2018,2019,2020년 회계 DB를 분리 |  |  |  |  | O
[2103-02] Separate DB from Account Menu |  | Account 메뉴의 연도별 DB 분리 | Kyle
[2103-03] Specify Expriration for Reward Point |  | 포인트에 대한 유효기간 지정
[2103-04] Showing Expired Date for Autodebit Menu | Showing autodebit active until DD/MM/YY in Autodebit menu | Autodebit 메뉴에서 DD/MM/YY까지 autodebit 활성화 표시 |  |  | Summer | Andrew Dibya |  |  | 2021-03-02 | 2021-03-08
[2103-05] BOK API |  |  |  |  | Bob |  |  |  | 2021-04-09 | 2021-04-30
[2103-06] BNI Bill Payment API | Bill Payment in Indonesia- API |  |  |  | Saroj Ram | Preyea Dibya
[2103-07] Commercial Bank API (New) |  | Third Party API 에서 신규 API로 분리 |  |  | Saroj Subash |  |  |  | 2021-03-04 | 2021-03-17
[2103-08] Tranglo API (New) |  | Third Party API 에서 신규 API로 분리 |  |  | Saroj Anil |  |  |  | 2021-03-04 | 2021-03-17
[2103-09] External Bank Routing |  |  | Saroj | [5 empty] | 2021-03-04 | 2021-03-11
[2103-10] Manual Gain Loss |  |  | Saroj
[2103-11] Peoples Bank API (Issue) | Receiver Name Can Single Name and Special Characters | 수신자 이름에 First Name도 가능하게 한다. 수신자 이름에 Special Character도 가능하게 한다. |  |  | Manoj |  |  |  | 2021-03-08 | 2021-03-12
[2103-16] Peoples Bank API v1.1 | Account Validation and Receiver Name Remove special character |  |  |  | Manoj |  |  |  | 2021-03-08 | 2021-03-12
[2103-12] Change logic for Local Topup |  | 1) 가상계좌 잔액을 업데이트 하지 않고, 국내 Topup을 할 수 있도록 로직 변경 2) 선불충전결과를 콜백으로 받지 못한 경우에, 고객의 요청으로 결과를 확인하는 기능
[2103-13] Notification for Smart Deposit |  | 편의점 입금이 성공하면, 앱에 알림을 줄수 있도록 하는 기능 1) Push Notification 으로 알리는 방법 2) SMS 으로 알리는 방법
[2103-14] ReDesign ProcessId for KFTC_DOMESTIC_HISTORY |  | 1) KFTC_DOMESTIC_HISTORY 테이블의 ProcessId 가 중복에 대한 해결로 YYYYMMDDHHMMSSFFF + customerId 로 변경 2) 기존 로직 확인 및 테스트 |  |  | Kyle |  |  |  | 2021-03-15 | 2021-03-19
[2103-15] Remove Charge Reward Point |  | 리워드 포인트를 구매하는 기능을 삭제, 리워드 포인트는 무상으로만 제공
[2103-17] Accounting Report Validation, Supplementation |  | Account 메뉴의 보고서 검증 및 보완
[2103-18] Renewal for GME Remittance Homepage (Korean) |  | GMERemittance 홈페이지를 한국어 버전의 리뉴얼 |  | Summer
[2103-19] OCR function in Mobile App |  | 모바일앱에서 OCR 기능을 사용해서 회원가입 및 정보수정
[2103-20] 2020 Account Data for Accounting Audits |  | 회계감사용 전표데이타 정합 |  |  |  |  | Max |  |  |  | 2021-03-16
[2103-21] New Policy to Stop Voice Phishing |  | 1) 신규가입한 고객은 D+7일동안 캄보디아, 몽골로 송금 금지 2) 신규가입한 고객은 D+7일동안 국내송금 금지 |  |  |  |  | Manoj |  |  |  | 2021-03-17
[2103-22] Editable in Manual Entry(OFAC) |  | 1) Remittance > OFAC Management > Manual Entry(OFAC) 메뉴에서 수정이 가능한 기능을 추가 | Manoj
[2103-23] Pop up for Preventing Violation |  |  |  |  | Kyle | Andrew/Dibya
[2103-24] Change SMS after Registration |  | 1) GME : Congratulations Send Your 1st transaction with Zero service charge 2) GME : You Can Send Money to Mongolia or Cambodia after [2021-03-24] | Kyle | [5 empty] | 2021-03-23 | 2021-03-23
[2103-25] Auto debit with GME Pass
[2103-26] Customer Balance History |  | 1) Customer Balance update in our system 2) 1분이내에 중복이 발생하면, 처리하지 않는다. |  |  |  |  | Manoj |  | 2021-03-15
[2103-27] Change Online Customers in Core System |  | 1) Online Customers > Online Remit > Approve Pending 2) Online Customers > Online Remit > Verify Pending 에서 Remarks 필드를 추가
[2103-28] Show notification by Provider Service |  | 1) 서비스별 점검에 대한 알림 기능 추가 2) 전체 서비스가 중지되지 않고, 특정 서비스만 중지될 수 있도록 기능을 구현
[2103-29] Siam Commercial Bank API
[2104-01] Receive Inbound through Partner API | Support to receive inbound from partner through pull method like E9Pay | E9Pay와 같은 방식으로 인바운드 수신 지원 | O |  | O | O
| Allow Customers to requrest to change 1. Beneficiary Name, Beneficiary Address, Beneficiary Mobile no. receiving Bank Name, Receiving Bank Branch Name, Receiving Account no. and send email and approval request in Admin system to that country CS | 고객의 정보를 수정하는 페이지?? | O
| make it possible to delete notices in notice board of customers app (all the customers once and one by one too) | Notice, Notification 에 대한 고객의 삭제기능 추가 | O |  | O | O
| Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Notice, Notification을 분리하는 기능 | O |  | O | O
| Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | 고객이 로그인할 때, 하루에 2번 팝업으로 안내 | O |  | O | O
| Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | 공지사항 및 알림의 두개의 탭 | O |  | O | O
| Notification popup after login [to support marketing part] |  | O |  | O | O
| Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | 새로운 알림에 대한 벨아이콘 표시하는 기능 |  |  | O | O
| Notification sort by date & time (The latest one need to be on the top) |  |  |  | O | O
| send transaction status once paid to sender as a push notification | 해외송금이 완료되어서 받는사람이 PAID하면, 송금인에게 Push Notification을 보내는 기능 | O |  | O
| Enable to check the promotions on mobile app |  | O |  | O | O
| Search the Domestic transaction by GME Control No. just like international Txn | GME Control No를 이용해서 국내송금을 검색하는 기능 | O
| Develop SMS function using kakaotalk notification | 카카오톡을 이용한 SMS기능 | O |  | O |  | O
| Make it possible to see customers basic info including bank A/C and their ID Photos (small preview) from the app | 모바일앱에서 은행계좌번호와 사진 등을 포함한 기본정보를 보여주는 기능 |  |  | O | O
| Bill Payment in Indonesia- API |  |  |  | O
| Push notification with picture and links. | 이미지와 링크를 포함하는 Push Notification 기능 | O |  | O | O
| Location Based Push notification | 지역별로 전송할 수 있는 Push Notification 기능 | O |  | O | O
| Schedule Bulk push notification/ Personal notification with "Name" |  | O |  | O | O
| Support to receive inbound from partner through pull method like E9Pay | E9Pay와 같은 방식으로 인바운드 수신 지원 | O |  | O | O
| Add Commercial Bank transactions to "transaction manual reprocess" menu | Menu name " Manual Reprocess" already Done
| Show the business days on App (CB/KBZ - real time, Others - 3~5 days) for Myanmar Only --> Country wise payout bank wise payout partnerwise different setup is necessary | 모바일앱에서 영업일을 표시?? | O |  | O | O
| BRAC Bank API | BRAC Bank API |  |  | O
| Stock Reports details Menu in core system |  | O
| Manual Reprocess menu with role defined by Country wise | 국가별 역할이 정의된 수동 재처리 메뉴? | O
| Hold Transaction(Temp) list role defined by countrywise | 국가별로 정의된 Hold Txn 목록? | O
| Transaction status Modification request to payment |  | O
| Transaction status Cancel request to Payment |  | O
| There should be reward point statement in the mobile app as well as admin menu | 모바일앱과 관리메뉴에 보상포인트 문구? | O |  | O | O
| Showing autodebit active until DD/MM/YY in Autodebit menu | Autodebit 메뉴에서 DD/MM/YY까지 autodebit 활성화 표시 | O |  | O | O
| Show record of rejected transaction sent from GME wallet, ( show record of failed txns) requested by Halimat | GME 지갑에서 발송된 거부된 트랜잭션의 레코드 표시 | O
| Reciepient save based on the most recent transfer - Send Money --> New Recipient | 가장 최근의 전송에 기반한 수취인 절약 - 송금 --> 새 수취인 |  |  |  | O
| Push notification available to unregistered customers too. All mobiles that have GME app should be able to get push notification notice | 미등록 고객도 푸시 알림을 사용할 수 있습니다. GME 앱이 있는 모든 모바일은 푸시 알림 통지를 받을 수 있어야 합니다. |  |  | O | O
| Add 50% off service fee coupon too | 서비스 수수료 50% 할인 쿠폰도 추가 |  |  |  |  | O
| Add info icon near Kwangju bank (On first screen)/GME Wallet (In Choose Payment Method) where customer can check to see how to use Kwangju bank after registration | 광주은행(첫 화면)/GME지갑(결제선택) 주변에 정보 아이콘 추가 등록 후 광주은행 이용방법 확인 가능 |  |  |  | O
International Top-up for Iphone
| Send Mongolian Name in 2 fields (First name and Last name seperately | 몽골 이름을 2개 필드로 전송(이름과 성을 별도로 전송) | O |  | O
| Domestic transaction ability to dowload receipt (Same as mobile) | 국내거래로 영수증 다운로드 가능(모바일과 동일) |  |  | O | O
| Inbound transaction receipt on the app FSOS Mongolia | FSOS 몽골 앱의 인바운드 트랜잭션 수신 | O |  | O | O
| Account Statement for Inbound txn | Need to have menu in admin system to see the customer inbound txn | O
| Report for inbound txn, need to show all txn | Now only shows 100 txn | O
| In smart CV deposit amount, initial deposit amount should not be included (If you press 50k, it should be 50k not 60k)- first time it should be 50K but if second time press then can be 100k | 스마트 CV 입금금액에는 최초 입금금액이 포함되지 않아야 합니다(50k를 누르면 60k가 아니라 50k여야 함). 10,000 또는 50,000을 누를 때마다 추가 기능을 제거합니다. |  |  |  | O
| KoronaPay - Kazakhstan Card Payment divide local currency and USD( modification required in API) | KoronaPay - 카자흐스탄 카드 결제 시 현지 통화와 USD 구분(API에서 수정 필요) |  |  | O
| Branches should include working hours, configurable from Admin System | 지점에는 관리 시스템에서 구성할 수 있는 근무 시간이 포함되어야 합니다. | O |  | O | O
| Push Notification received multiple times (Fix the issue) | 여러 번 수신한 푸시 알림(문제 해결) |  |  | O
| Both IOS and Android password login page should have CS button (when the KFTC security keyboard appears , there also should be Call icon ) | IOS 및 Android 암호 로그인 페이지에는 모두 CS 버튼이 있어야 합니다(KFTC 보안 키보드가 나타나면 통화 아이콘도 있어야 함). |  |  |  | O
| Both IOS and Android password login page should have password reset button | IOS 및 Android 암호 로그인 페이지에는 모두 암호 재설정 버튼이 있어야 합니다. |  |  | O | O
| Account name verification should be automatic with primary & secondary ID (Now we are manually changing passport and ID Card) | 계정 이름 확인은 기본 및 보조 ID와 함께 자동으로 이루어져야 합니다(이제 수동으로 여권 및 ID 카드를 변경하고 있습니다). | O |  | O
| Reward Points Statement showing when it was earnt and when it will expire | 획득 시기와 만료 시기를 보여주는 보상 포인트 명세서 | O |  | O | O
| Replace the 'Error Message: "You donot have sufficient balance to do the transactions"' into "Please deposit the amount to Kwangju bank *customer's virtual bank account* first"and translate into Vietnamese. | 오류 메시지: "거래 잔고가 충분하지 않습니다"를 "광주은행 *고객의 가상계좌*에 먼저 입금해 주십시오"로 대체하고 베트남어로 번역한다. |  |  | O
| Translate transaction status Paid/Cancel/Processing/Failed/Success into local languages | 거래 상태를 결제/취소/처리/실패/성공으로 변환(?) | O |  | O | O
| Translate Relation and Transfer Reason into local languages. | ?? | O |  | O
| When clicking on GME notification on phones, it should directly go to that Notice, not the App. | Notification을 누르면, 상세페이지로 이동 | O |  | O | O
| Show Sender name and receiver name for GME Wallet statement whenever available | GME Wallet Statement에서 보낸사람/받는사람의 이름을 표시 | O |  | O | O
| Add 'Instruction' for Convenience Store Deposit and Smart Withdraw | 모바일앱의 사용방법에 대한 설명을 하는 기능 |  |  |  | O
| Promotion page inside the app: Add Image Carousel Sliders of Promotions into the Home page. When clicked, details of promotions will be shown in Menu -> Promotions. | Like the hanpass app | O |  | O | O
| Add Registration Tutorials video in local languages under New User and Login buttons after language is selected. | ?? |  |  |  | O
| Adding receiving bank (myanmar bank) Logo | 미얀마은행의 로고를 추가 | O |  | O | O
| New Individual referral code for everyone |  | O |  | O | O
| Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | 모바일앱을 다운로드했지만, 가입하지 않은 고객에 대한 Push Notification |  |  | O | O
| EMI for GME Finance Calculate from mobile app |  | O |  | O | O
| Check GME Finance loan statement from mobile app |  | O |  | O | O
| Withdraw Money from All ATMs | 모든 ATM기기에서 출금이 가능한 기능 | O |  | O | O
| 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다. | 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다. | O |  | O | O
| 에러메시지 내용의 효율성 - 해당현상이 반복되는 경우 고객센터로 문의해 주세요. - 전화문의, 카카오톡 |  |  |  | O
| Bank of Korea Reporting through Fintech Association System API |  | O
| Route Txn based on Amount |  | O
AYA Bank API
[2101-S01] Setup Douzone Solution |  | 1) 더존솔루션을 설치할 서버세팅(IP, FW…) | [5 empty] | Dana
[2101-S02] Mass Email System |  | 1) info@gmeremit.com 이메일을 이용한 이메일이 왜 늦게 전송되는지 원인에 대한 파악 및 해결 2) 대용량 메일 시스템에 대한 조사 | [5 empty] | Dana
[2101-S03] Change DNS Provider |  | 1) gmeremit.com 의 DNS 제공업체 분석 및 교체에 대한 분석 | [5 empty] | Dana
[2101-S04] Change DNS Provider |  | 1) gmeremit.com 의 DNS 제공업체 분석 및 교체에 대한 분석 | [5 empty] | Dana
[2101-S05] 전자금융업 금감원 1분기 보고 | [7 empty] | Dana
[2102-S01] Make VM for DB Data Backup |  | DB Data의 사내백업용 VM을 추가하고, FTP로 백업을 진행 | [5 empty] | Dana | 2021-02-09 | 2021-02-09
[2102-S06] Manual for Emergency Recovery |  | 응급복구 매뉴얼 작성 | [5 empty] | Max | 2021-03-02 | 2021-03-19
[2102-S07] Manual for Security Task List |  | 보안관련 업무 리스트 제작 | [5 empty] | Dana | 2021-02-25 | 2021-03-05
[2103-S01] GME IT Compliance System Construction-v1.0 |  | GME IT Compliance 시스템 구축 1) 감사기준 대분류.중분류.소분류 코드 제작 2) 공통, 오픈뱅킹, 전자금융, ISMS별 문서관리 3) 과제 점검 및 체크리스트 제작 및 관리 | [5 empty] | Dana | 2021-03-17 | 2021-03-31
[2103-S02] Personal Information FlowChart |  | 1. GME 개인정보 수집, 보유 및 이용흐름표 v1.0 2. GME 개인정보 제공, 파기 흐름표 v1.0 | [5 empty] | Dana | 2021-03-17 | 2021-03-22
[2104-S01] Collect Windows Event Log |  | 1. 서버에서 발생하는 이벤트 로그에 대한 수집 2. 저장방식(DB, File) 에 대한 설정
[2104-S02] 전자금융업 중계기관 연동 |  | 1. 전자금융업을 하고 있는 이용사는 코스콤 중계기관과 VPN연동 | [5 empty] | Ravindra | 2021-04-08 | 2021-04-30
[2104-S03] 보유중인 VPN장비에 대한 파악 |  | 1. 보유중인 VPN장비 파악 2. 계정정보 파악 3. 모니터링 확인 방법 파악 | [5 empty] | Ravindra | 2021-04-08 | 2021-04-16
[2104-S04] GME Finance 신용정보취급 자체평가 보고 |  | https://assess.fsec.or.kr/assess/self/assessPrgs.do
[2104-S05] GME Finance IPSEC VPN SETUP |  | GME대부와 코스콤 금융클라우드 IDC간 IPSEC VPN세팅 작업(위드네트웍스)
[2103-Q01-01] |  | (안드로이드) 해외송금 영수증에서 Total Sent Amount가 1원이 더 표시되는 경우가 있음
[2103-Q01-02] |  | (안드로이드) 기간검색에 대한 오류
[2103-Q01-03] |  | (안드로이드) 해외Topup 서비스에서 오류메시지 원인분석 및 해결
[2103-Q01-04] |  | (안드로이드) 환율조회 에러에 대한 원인분석 및 해결
[2103-Q01-05] |  | (안드로이드) 이용약관 파일 오동작에 대한 원인 분석 및 해결
[2103-Q01-06] |  | (안드로이드) 국내송금에서 Autodebit 선택시 최근목록에서 GME Wallet의 이력을 제외시키는 기능
[2103-Q01-07] |  | (안드로이드) 테스트버전에서 해외Topup서비스에 대한 확인
[2103-Q01-08] |  | (안드로이드) 쿠폰 구매시 지점명 확인 및 해결
[2103-Q01-09] |  | (안드로이드) GME Wallet Statement 정렬
[2103-Q01-10] |  | (안드로이드) Smart Deposit에서 비밀번호가 틀렸을때, 메시지 변경
[2103-Q03-01] |  | (관리자) 회원가입시 IdType의 순서를 앱과 동일하게 하는 기능
[2103-Q03-02] |  | (관리자) KJ API > Customer ID Verification 에서 DOB 원인분석 및 해결
[2103-Q03-03] |  | (관리자) ADMINISTRATION > Customer Management > Reward Point Management
[2103-Q03-04] |  | (관리자) PDF 다운로드 기능에 대한 확인 및 해결
[2103-Q03-05] |  | (관리자) Coupon Issue Display
[2103-Q04-01] |  | (Online) Web에서 보이는 dob값이 Android를 통한 dob 값과 불일치에 대한 원인분석 및 해결
[2103-Q05-01] |  | (서버) Application_Log.ApplicationLogger.Message필드를 NVARCHAR로 변경
[2104-Q05-01] Alipay Status Synchronize |  | (서버) Ali Pay Status Synchronize Problem
Q1 | 안드로이드
Q2 | iOS
Q3 | Core
Q4 | Online
Q5 | Server

## 2021-Q2
2021년 2분기 프로젝트
Q1 | 안드로이드
Q2 | iOS
Q3 | Core
Q4 | Online
Q5 | Server
Project Code(Name) | Description | 설명 | UI/UX | Core | Online | Server/API | Mobile | Other | Infra | 시작일 | 목표일 | 종료일 | 배포일
[2007-10] Setup GitLab and SVN in Korea | Setup GitLab and SVN in Korea | [6 empty] | Kyle
[2009-02] Seperate Relationship list from Oversear Txn | [2009-02]- Seperate Relationship list from Overseas Txn |  |  | O
[2011-01] Auto Remit with Korea-Seven | Auto Remit with Korea Seven |  |  | JY |  | JY |  |  |  | 2021-01-18 | 2021-01-20
[2012-05] Translation for Bank Names in native language with bank logo | Translation for Bank Names in native language with bank logo | 은행로고가 있는 다국어로 은행을 표시 |  | Saroj |  | Saroj | Preyea Dibya |  |  | 2021-02-08 | 2021-02-26
[2012-11] Upload New Photo in Admin Page | include a button in Admin System to request to upload new photos. then we don't need to request photos but request them to upload | ID Card.를 업로드하는 기능 |  | O |  | O | O
[2012-14] Admin Menu to Hold RealTime Txn | Admin Menu to hold realtime Txn |  |  | O |  | O
[2012-16] Admin Page for KJ Bank Deposit Error | Admin Page for KJ Bank Deposit error | 광주은행 입금실패에 대한 원인을 제공하는 관리자 페이지
[2101-08] SIGUE Inbound API | SIGUE Inbound API |  |  | Saroj |  | Manoj Ram |  |  |  | 2021-01-18 | 2021-02-10
[2101-23] KoronaPay Inbound API |  |  |  | Saroj |  | Anil Ram | Preyea Dibya |  |  |  | 2021-01-25
[2102-11] Core logic for Inbound API | Dynamic API Routing and Core Inbound Functionality | [6 empty] | Saroj |  | 2021-02-10 | 2021-02-25
[2102-06] Inbound Transaction pay API Endpoints | Features that can be checked on the Mobile App when an Inbound remittance is received | Inbound송금이 들어오면, Mobile App에서 확인이 가능한 기능 |  |  |  | Saroj | Preyea Dibya | Saroj |  |  |  | Android: Done iOS: on going
[2101-09] Change Upload Location for ID Card Image |  | 신분증 이미지 업로드 패스 변경 |  | Kyle | Kyle | Kyle |  |  |  | 2021-01-18 | 2021-01-29 | 2021-01-29(개발)
[2101-28] Upload Customer Document from Core System | Provide an administrator page where you can request the customer's ID Card image again. Employees re-request ID Card images from the Admin page to the customer The customer checks the ID Card image request in the app and uploads the ID Card image. | 고객의 ID Card이미지를 다시 요청할 수 있는 관리자페이지 제공 직원은 관리자페이지에서 고객에게 ID Card이미지를 다시 요청 고객은 앱에 팝업으로 ID Card이미지 요청을 확인하고, ID Card이미지를 업로드한다. |  | Manoj |  | Manoj | Preyea Dibya |  |  | 2021-01-15 | 2021-02-04 | Android: Done iOS: not start
[2102-08] Separating for Notice and Notification |  | 1. 현재 Notice 의 기능을 Notice 와 Notification 으로 분리해서 운영 2. Notice는 삭제되지 않고, Notification은 고객의 요청에 의해서 삭제할 수 있다. 3. 새로운 Notice에 대해서 벨아이콘으로 표시하는 기능 4. Notice와 Notification은 날짜에 의해서 정렬이 가능하도록 5. Notice와 Notification은 제목과 내용에 의해서 검색이 가능하도록 6. 새로운 Notice는 고객이 로그인할때, 하루에 2번 팝업으로 안내할 수 있는 기능 7. 영업직원이 Notification 팝업메시지를 전송할 수 있는 기능
[2102-15] KFTC FinTech Information Provider API |  | 오픈뱅킹 핀테크업 정보제공자 API |  |  |  | JY |  |  |  | 2021-05-03 | 2021-05-21
[2103-01] Archive Old Accounting DB | Archive 2017, 2018 and 2019 Accounting DB to separate DB | 2017,2018,2019,2020년 회계 DB를 분리 | [5 empty] | O
[2103-02] Separate DB from Account Menu |  | Account 메뉴의 연도별 DB 분리
[2103-03] Specify Expriration for Reward Point |  | 포인트에 대한 유효기간 지정
[2103-05] BOK API | [5 empty] | Bob |  |  |  | 2021-04-09 | 2021-04-30
[2103-06] BNI Bill Payment API | Bill Payment in Indonesia- API |  |  |  |  | Saroj Ram | Preyea Dibya
[2103-08] Tranglo API (New) |  | Third Party API 에서 신규 API로 분리 |  |  |  | Saroj Anil |  |  |  | 2021-03-04 | 2021-03-17
[2103-12] Change logic for Local Topup |  | 1) 가상계좌 잔액을 업데이트 하지 않고, 국내 Topup을 할 수 있도록 로직 변경 2) 선불충전결과를 콜백으로 받지 못한 경우에, 고객의 요청으로 결과를 확인하는 기능
[2103-13] Notification for CVS Deposit |  | 편의점 입금이 성공하면, 앱에 알림을 줄수 있도록 하는 기능 1) Push Notification 으로 알리는 방법 2) SMS 으로 알리는 방법 |  |  |  | Summer | Andrew Dibya |  |  | 2021-05-04 | 2021-05-07
[2103-14] ReDesign ProcessId for KFTC_DOMESTIC_HISTORY |  | 1) KFTC_DOMESTIC_HISTORY 테이블의 ProcessId 가 중복에 대한 해결로 YYYYMMDDHHMMSSFFF + customerId 로 변경 2) 기존 로직 확인 및 테스트 | [7 empty] | 2021-03-15 | 2021-03-19
[2103-15] Remove Charge Reward Point |  | 리워드 포인트를 구매하는 기능을 삭제, 리워드 포인트는 무상으로만 제공
[2103-19] OCR function in Mobile App |  | 모바일앱에서 OCR 기능을 사용해서 회원가입 및 정보수정
[2103-25] Auto debit with GME Pass
[2103-26] Customer Balance History |  | 1) Customer Balance update in our system 2) 1분이내에 중복이 발생하면, 처리하지 않는다. | [5 empty] | Manoj |  | 2021-03-15
[2103-27] Change Online Customers in Core System |  | 1) Online Customers > Online Remit > Approve Pending 2) Online Customers > Online Remit > Verify Pending 에서 Remarks 필드를 추가
[2103-28] Show notification by Provider Service |  | 1) 서비스별 점검에 대한 알림 기능 추가 2) 전체 서비스가 중지되지 않고, 특정 서비스만 중지될 수 있도록 기능을 구현
[2103-29] Siam Commercial Bank API
[2103-30] Check Real Name in Inbound Account |  | 1) 인바운드 계좌 등록에서 실명조회를 하는 기능을 추가
[2104-01] Receive Inbound through Partner API | Support to receive inbound from partner through pull method like E9Pay | E9Pay와 같은 방식으로 인바운드 수신 지원 |  | O |  | O | O
[2104-02] GME-Pay Notice at Online |  | 선불충전금 운영현황 홈페이지 공시 |  |  | Summer |  |  |  |  | 2021-04-19 | 2021-04-19
[2104-03] Make UI/UX GuideLine |  | 현재 시스템의 UI/UX 가이드 라인 제작 | Meghan | [6 empty] | 2021-04-19 | 2021-05-18
[2104-04] Make Design Prototype |  | 현재 시스템의 포로토타입 제작 | Meghan | [6 empty] | 2021-04-19 | 2021-05-18
[2104-05] Complement Design by current Service |  | 현재 서비스별 디자인 보완(버튼, 치수 등) | Meghan
[2104-06] Make New Design System |  | 새로운 디자인 시스템 구축(전체적인 화면 구성, 컬러 등) | Meghan
[2104-07] TerraPay API v2.0 |  | Nigeria : Bank Deposit Liberia : Bank Deposit Ghana : Mobile Wallet Tanzania: Bank Deposit |  | Manoj
[2104-08] Country wise reprocess control for users |  |  |  | Saroj | [5 empty] | 2021-04-15 | 2021-04-20
[2104-09] Cebuana API v2.0 | Remittance Update, RTA Transaction Update |  |  | Saroj | [5 empty] | 2021-04-26 | 2021-04-30
[2104-10] Change for Remittance voucher generate | To avoid duplicate voucher generate | 이중 전표에 대한 방지 로직 추가 |  | Saroj | [5 empty] | 2021-04-26 | 2021-05-04
[2104-11] Changing the logic for Permission | [6 empty] | Andrew Dibya |  |  | 2021-04-26 | 2021-04-30
[2105-01] Koscom Information Provider API |  | 코스콤 중계기관 이용사 정보 제공 API |  |  |  | Bob |  |  |  | 2021-05-03 | 2021-05-21
[2105-02] Referral Page Update |  |  |  | Summer | [5 empty] | 2021-05-07 | 2021-05-13 |  | 2021-05-31
[2105-03] 운영/테스트/개발 환경 분리 |  | 1) 운영/개발/테스트 환경 분리 2) 운영/개발/테스트 개발 소스 분리 및 동기화 작업 | [7 empty] | 2021-05-03 | 2021-05-07
[2105-04] Remove Refferal Code |  | 1) 앱에서 추천인코드는 보이지 않게 처리 |  |  |  | Manoj |  |  |  | 2021-05-12 | 2021-05-12
[2105-05] Currency wise txn valiation for Srilanka |  | 1) 고객이 등록한 수취인계좌의 입금이 USD만 가능한지, LKR만 가능한지 확인해서 송금을 시도한다. |  |  |  | Manoj |  |  |  | 2021-05-12 | 2021-05-13
[2105-06] Improve for Splash Screen |  | 1) 스플래쉬 스크린과 메인 스크린을 분리하면서 성능 향상 |  |  |  |  | Andrew Dibya |  |  | 2021-05-13 | 2021-05-17
[2105-07] Change name of bank |  | 오픈뱅킹 등록하는 은행이름을 KFTC에서 제공하는 이름으로 변경 |  |  |  |  | Andrew Dibya
[2105-08] Cancellation of Alipay API
[2105-09] Change Path for IDCard Image |  | ID Card 이미지의 경로를 변경
[2105-11] Preview image in the Notification |  | 1) Notification을 받았을 때, Indicator에서 Preview로 이미지 표현 |  |  |  | Summer | Andrew Dibya |  |  | 2021-05-24 | 2021-05-25
[2105-12] Separate for SMS Agent Server |  | 1) 벌크용 SMS와 정보용 SMS를 분리해서 고객들에게 SMS가 늦게 도착하는 문제를 보완
[2105-13] Make Prototype for competitor |  | 경쟁사(E9Pay, Hanpass, Gmoney, WireValley, CentBe) 분석 1) 시나리오 영상제작 2) 프로토타입 제작 | Meghan | [6 empty] | 2021-05-24 | 2021-06-30
[2105-14] Remarks Add Display in AgentPortal |  |  |  | Manoj | [5 empty] | 2021-05-20 | 2021-0524 | 2021-05-24
[2105-15] Manage for Multi-Language |  |  |  | Subash | [5 empty] | 2021-05-27 | 2021-06-02
[2105-16] Analysis and demonstration of snapcall |  | SnapCall에 대한 분석 및 데모 제작 |  |  |  |  | Andrew |  |  | 2021-05-31 | 2021-06-11
[2105-17] Upgrade for Android Progress |  | 안드로이드에서 프로그레스가 깜빡이는 현상에 대한 보완 1) 프로그레스 이미지 보완 2) 프로그레스가 깜빡이는 현상에 대한 개발 보완 | Meghan |  |  |  | Andrew |  |  | 2021-05-31 | 2021-06-11
[2105-18] New Voice Phishing v2.0 |  |  |  | Manoj | [5 empty] | 2021-05-31 | 2021-06-04
[2105-19] GME Finance Icon in GME App |  |  | Meghan | [6 empty] | 2021-06-01 | 2021-06-04
[2106-02] Change Bank Statement able to see in 3-Months |  | 오픈뱅킹 조회에서 은행계좌 조회를 3개월까지 가능하도록 변경
[2106-03] Add guide for Store Deposit |  | 편의점 입금화면에서 가이드를 제공
[2106-04] Change information in Wallet Statement |  | 1) 받은 사람의 리스트에는 보낸사람이름, 날짜, 시간, 금액을 출력 2) 받을때 +, 보낼때 -를 붙여서 출력 3) 남은 잔액을 출력
[2106-06] Application Deposit to KJ Bank Wallet |  | 광주은행 가상계좌에 입금신청 메뉴 및 신청조회 메뉴 추가 | Meghan | Manoj |  | Manoj | Andrew Dibya |  |  | 2021-06-04 | 2021-06-18
[2106-07] CI batch conversion and real-time conversion |  | 1) CI일괄변환
[2106-08] Multi-language with Lokalize |  | Lokalise를 이용한 다국어 앱을 개발 1) 데모 제작 2) 신규 기능에 적용 3) 기존 기능에 적용 |  |  |  |  | Andrew Dibya |  |  | 2021-06-08 | 2021-07-23
[2106-09] Convert from K7 to KJ |  | 코리아세븐 고객을 광주은행 고객으로 Convert하는 기능을 개발
[2106-10] Add Real-Name Module in Overseas Remittance |  | 해외송금에서 계좌송금인 경우에, 실명조회를 통해서 고객에게 수신인 이름을 팝업으로 제공한다.
[2106-01] Check for App Weak Point |  | 안드로이드와 IOS의 앱취약점 점검에 대한 보안대책 1) 기존에 있었던 앱취약점 점검 항목에 대한 개발 체크 2) 상반기 취약점 점검에 대한 대비 |  |  |  |  | Andrew Preyea Dibya |  |  | 2021-06-02 | 2021-06-25
[2106-11] 웹취약점 점검 |  | 1) 중요정보보호 - 메모리, DOM영역, 네트워크구간 노출여부 |  |  | Summer |  |  |  |  | 2021-06-10 | 2021-08-31
[2106-12] Add Snapcall in Mobile App |  | 1) 스냅콜 기능을 모바일폰(안드로이드, 아이폰)에서 구현 2) |  |  |  |  | Andrew Dibya |  |  | 2021-06-10 | 2021-06-18
[2106-13] ATM Withdraw with Coocon |  | 1) 쿠콘 API를 이용한 모든 편의점에서 출금가능한 서비스 | Meghan |  |  | Dhan | Preyea Dibya |  |  | 2021-06-15 | 2021-06-18
[2106-14] GME-Pay History Management by GME-Pay Charge | [5 empty] | JY
| Put GME Wallet no. in KJ Bank and CMS Bank Statement( Requested by Sagar for reconciliation) | KFTC를 이용한 송금의 전표에 가상계좌번호를 추가
| Download PDF receipt for inbound txn (for immigration use) | 인바운드 송금에 대한 PDF 영수증 다운로드
| Remaining Inbound txn Limit in USD have to show in app | 인바운드 송금의 한도를 표시
| Please provide smart deposit guideline as Gmoneytrans: Q1 | 편의점 입금에 대한 매뉴얼을 표시
| Mobile wallet should be seperated to bkash and rocket wallet due wallet digit issue | [방글라데시] 송금종류를 Cash, Bank, Wallet => Cash, Bank, Bkash Wallet, Rocket Wallet으로 변경
| Open Cash payment and Mobile wallet with Ly-hour | Lyhour를 이용해서 Cash, Mobile Wallet 송금이 가능하게
| Push Notification Rights to be given by country - Phillipines staff can only send to Phillipines | 각 국가의 마케팅 직원은 해당 국가로만 메시지를 보낼 수 있다
| add new column in verify pending menu/approve pending for the latest remarks. | [2103-27] Change Online Customers in Core System 으로 이미 등록되어 있음
| Receiving inbound transaction in wsb wallet with receiving limit of 1 mil txn per day. | WSB고객은 하루에 1MIL 의 Inbound를 받을 수 있도록 추가
Cancel button for Smart deposit
| Instructions for convenience store's staff (GME PAY), get the screenshot from the GS 7-11, CU in Korean language and put it in our app | 편의점 직원에 대한 지침
| Mobile App Language should be configurabale from admin system. | 모바일앱 언어는 관리자 시스템에서 구성할 수 있도록
| change the label '' enter last name " to "enter last name /Surname" | 수취인 정보에서 Last Name을 추가한다.
| Add Thunes logo in Transaction Receipt for Thunes Transaction (South Africa) | Tunes 트랜잭션에 Tunes 로고를 추가(남아프리카)
| Enable Sender to use saved reciever regardless of partner | 이미 송금한 수신인의 파트너가 바뀌어도 송금이 가능하도록 내부처리
| Sync partner txn status with GME status () | 파트너의 송금상태(Paid, Cancel, Processing)를 GME에서 동기화해서 보여줄 수 있도록 한다. 일부 파트너는 이미 제공하고 있음
| Wallet to Bank transfer should be Free only 10 times and after that charge 500 Won | 가상계좌에서 국내이체는 10번만 무료이고, 그이후에는 500원
| Show the list of receiver based on time wise, latest on the top. Initially while loading receiver only show latest 10 receivers. Also add Date button to display the no of receivers just like local Transfer( Subash ) | 수취인 등록에서 날짜를 기준으로 조회하고, 최근 보낸 사람순으로 정렬한다.
| Send email to customers every week to use their reward points | 매주 고객에게 이메일을 보내
| [Sapumal]While adding new beneficiary, Provide the name of the receiver that is received from partner as pop up, when customer click Confrim the auto populate the beneficiary name . | [스리랑카] 수취인 등록화면에서 수취인을 등록하면, Commercial Bank 에서 수취인 확인 API를 이용해서 이름을 팝업해서 확인하는 기능
| Allow Customers to requrest to change 1. Beneficiary Name, Beneficiary Address, Beneficiary Mobile no. receiving Bank Name, Receiving Bank Branch Name, Receiving Account no. and send email and approval request in Admin system to that country CS | 고객의 정보를 수정하는 페이지?? |  | O
| make it possible to delete notices in notice board of customers app (all the customers once and one by one too) | Notice, Notification 에 대한 고객의 삭제기능 추가 |  | O |  | O | O
| Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | Notice, Notification을 분리하는 기능 |  | O |  | O | O
| Notice should display as pop-up when customer login to the app ( 1 Notice should pop only max 2 times in 1 day) | 고객이 로그인할 때, 하루에 2번 팝업으로 안내 |  | O |  | O | O
| Mobile App: Two tab for Notice And Notification ( the Notice shouldn’t be able to delete, Notification should be able to delete by customer) | 공지사항 및 알림의 두개의 탭 |  | O |  | O | O
| Notification popup after login [to support marketing part] |  |  | O |  | O | O
| Bell icon in home page with showing the no. of new notificaitons in the bell icon itself | 새로운 알림에 대한 벨아이콘 표시하는 기능 |  |  |  | O | O
| Notification sort by date & time (The latest one need to be on the top) |  |  |  |  | O | O
| send transaction status once paid to sender as a push notification | 해외송금이 완료되어서 받는사람이 PAID하면, 송금인에게 Push Notification을 보내는 기능 |  | O |  | O
| Enable to check the promotions on mobile app |  |  | O |  | O | O
| Search the Domestic transaction by GME Control No. just like international Txn | GME Control No를 이용해서 국내송금을 검색하는 기능 |  | O
| Develop SMS function using kakaotalk notification | 카카오톡을 이용한 SMS기능 |  | O |  | O |  | O
| Make it possible to see customers basic info including bank A/C and their ID Photos (small preview) from the app | 모바일앱에서 은행계좌번호와 사진 등을 포함한 기본정보를 보여주는 기능 |  |  |  | O | O
| Bill Payment in Indonesia- API |  |  |  |  | O
| Push notification with picture and links. | 이미지와 링크를 포함하는 Push Notification 기능 |  | O |  | O | O
| Location Based Push notification | 지역별로 전송할 수 있는 Push Notification 기능 |  | O |  | O | O
| Schedule Bulk push notification/ Personal notification with "Name" |  |  | O |  | O | O
| Support to receive inbound from partner through pull method like E9Pay | E9Pay와 같은 방식으로 인바운드 수신 지원 |  | O |  | O | O
| Add Commercial Bank transactions to "transaction manual reprocess" menu | Menu name " Manual Reprocess" already Done
| Show the business days on App (CB/KBZ - real time, Others - 3~5 days) for Myanmar Only --> Country wise payout bank wise payout partnerwise different setup is necessary | 모바일앱에서 영업일을 표시?? |  | O |  | O | O
| BRAC Bank API | BRAC Bank API |  |  |  | O
| Stock Reports details Menu in core system |  |  | O
| Manual Reprocess menu with role defined by Country wise | 국가별 역할이 정의된 수동 재처리 메뉴? |  | O
| Hold Transaction(Temp) list role defined by countrywise | 국가별로 정의된 Hold Txn 목록? |  | O
| Transaction status Modification request to payment |  |  | O
| Transaction status Cancel request to Payment |  |  | O
| There should be reward point statement in the mobile app as well as admin menu | 모바일앱과 관리메뉴에 보상포인트 문구? |  | O |  | O | O
| Showing autodebit active until DD/MM/YY in Autodebit menu | Autodebit 메뉴에서 DD/MM/YY까지 autodebit 활성화 표시 |  | O |  | O | O
| Show record of rejected transaction sent from GME wallet, ( show record of failed txns) requested by Halimat | GME 지갑에서 발송된 거부된 트랜잭션의 레코드 표시 |  | O
| Reciepient save based on the most recent transfer - Send Money --> New Recipient | 가장 최근의 전송에 기반한 수취인 절약 - 송금 --> 새 수취인 |  |  |  |  | O
| Push notification available to unregistered customers too. All mobiles that have GME app should be able to get push notification notice | 미등록 고객도 푸시 알림을 사용할 수 있습니다. GME 앱이 있는 모든 모바일은 푸시 알림 통지를 받을 수 있어야 합니다. |  |  |  | O | O
| Add 50% off service fee coupon too | 서비스 수수료 50% 할인 쿠폰도 추가 | [5 empty] | O
| Add info icon near Kwangju bank (On first screen)/GME Wallet (In Choose Payment Method) where customer can check to see how to use Kwangju bank after registration | 광주은행(첫 화면)/GME지갑(결제선택) 주변에 정보 아이콘 추가 등록 후 광주은행 이용방법 확인 가능 |  |  |  |  | O
International Top-up for Iphone
| Send Mongolian Name in 2 fields (First name and Last name seperately | 몽골 이름을 2개 필드로 전송(이름과 성을 별도로 전송) |  | O |  | O
| Domestic transaction ability to dowload receipt (Same as mobile) | 국내거래로 영수증 다운로드 가능(모바일과 동일) |  |  |  | O | O
| Inbound transaction receipt on the app FSOS Mongolia | FSOS 몽골 앱의 인바운드 트랜잭션 수신 |  | O |  | O | O
| Account Statement for Inbound txn | Need to have menu in admin system to see the customer inbound txn |  | O
| Report for inbound txn, need to show all txn | Now only shows 100 txn |  | O
| In smart CV deposit amount, initial deposit amount should not be included (If you press 50k, it should be 50k not 60k)- first time it should be 50K but if second time press then can be 100k | 스마트 CV 입금금액에는 최초 입금금액이 포함되지 않아야 합니다(50k를 누르면 60k가 아니라 50k여야 함). 10,000 또는 50,000을 누를 때마다 추가 기능을 제거합니다. |  |  |  |  | O
| KoronaPay - Kazakhstan Card Payment divide local currency and USD( modification required in API) | KoronaPay - 카자흐스탄 카드 결제 시 현지 통화와 USD 구분(API에서 수정 필요) |  |  |  | O
| Branches should include working hours, configurable from Admin System | 지점에는 관리 시스템에서 구성할 수 있는 근무 시간이 포함되어야 합니다. |  | O |  | O | O
| Push Notification received multiple times (Fix the issue) | 여러 번 수신한 푸시 알림(문제 해결) |  |  |  | O
| Both IOS and Android password login page should have CS button (when the KFTC security keyboard appears , there also should be Call icon ) | IOS 및 Android 암호 로그인 페이지에는 모두 CS 버튼이 있어야 합니다(KFTC 보안 키보드가 나타나면 통화 아이콘도 있어야 함). |  |  |  |  | O
| Both IOS and Android password login page should have password reset button | IOS 및 Android 암호 로그인 페이지에는 모두 암호 재설정 버튼이 있어야 합니다. |  |  |  | O | O
| Account name verification should be automatic with primary & secondary ID (Now we are manually changing passport and ID Card) | 계정 이름 확인은 기본 및 보조 ID와 함께 자동으로 이루어져야 합니다(이제 수동으로 여권 및 ID 카드를 변경하고 있습니다). |  | O |  | O
| Reward Points Statement showing when it was earnt and when it will expire | 획득 시기와 만료 시기를 보여주는 보상 포인트 명세서 |  | O |  | O | O
| Replace the 'Error Message: "You donot have sufficient balance to do the transactions"' into "Please deposit the amount to Kwangju bank *customer's virtual bank account* first"and translate into Vietnamese. | 오류 메시지: "거래 잔고가 충분하지 않습니다"를 "광주은행 *고객의 가상계좌*에 먼저 입금해 주십시오"로 대체하고 베트남어로 번역한다. |  |  |  | O
| Translate transaction status Paid/Cancel/Processing/Failed/Success into local languages | 거래 상태를 결제/취소/처리/실패/성공으로 변환(?) |  | O |  | O | O
| Translate Relation and Transfer Reason into local languages. | ?? |  | O |  | O
| When clicking on GME notification on phones, it should directly go to that Notice, not the App. | Notification을 누르면, 상세페이지로 이동 |  | O |  | O | O
| Show Sender name and receiver name for GME Wallet statement whenever available | GME Wallet Statement에서 보낸사람/받는사람의 이름을 표시 |  | O |  | O | O
| Add 'Instruction' for Convenience Store Deposit and Smart Withdraw | 모바일앱의 사용방법에 대한 설명을 하는 기능 |  |  |  |  | O
| Promotion page inside the app: Add Image Carousel Sliders of Promotions into the Home page. When clicked, details of promotions will be shown in Menu -> Promotions. | Like the hanpass app |  | O |  | O | O
| Add Registration Tutorials video in local languages under New User and Login buttons after language is selected. | ?? |  |  |  |  | O
| Adding receiving bank (myanmar bank) Logo | 미얀마은행의 로고를 추가 |  | O |  | O | O
| New Individual referral code for everyone |  |  | O |  | O | O
| Customer who downloaded mobile app and didn’t use, Tracking those customers and sending them push messages | 모바일앱을 다운로드했지만, 가입하지 않은 고객에 대한 Push Notification |  |  |  | O | O
| EMI for GME Finance Calculate from mobile app |  |  | O |  | O | O
| Check GME Finance loan statement from mobile app |  |  | O |  | O | O
| Withdraw Money from All ATMs | 모든 ATM기기에서 출금이 가능한 기능 |  | O |  | O | O
| 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다. | 회원가입후, 계정을 인증하는동안 안내하는 멘트를 추가 -최대 6시간이 소요될 예정입니다.현재 담당 직원이 신분증을 확인 중에 있습니다. 기타 문의는 카카오톡 혹은 채팅 상담이 24시간 가능합니다. |  | O |  | O | O
| 에러메시지 내용의 효율성 - 해당현상이 반복되는 경우 고객센터로 문의해 주세요. - 전화문의, 카카오톡 |  |  |  |  | O
| Bank of Korea Reporting through Fintech Association System API |  |  | O
| Route Txn based on Amount |  |  | O
AYA Bank API
[2105-Q3] Add Control No for International and Local Topup into Customer account Statement | Admin Account Statement needs to show co.number for DT, International and Domestic TOPUP (E.g. DT-Wallet Deposit - 202102083832728372) | Account> Account Statement 에서 Particulars에 ControlNo(ProcessId)를 추가한다. (국내송금, 국내외 TOPUP)
[2101-S02] Mass Email System |  | 1) info@gmeremit.com 이메일을 이용한 이메일이 왜 늦게 전송되는지 원인에 대한 파악 및 해결 2) 대용량 메일 시스템에 대한 조사 | [6 empty] | Dana
[2101-S03] Change DNS Provider |  | 1) gmeremit.com 의 DNS 제공업체 분석 및 교체에 대한 분석 | [6 empty] | Dana
[2101-S04] Change DNS Provider |  | 1) gmeremit.com 의 DNS 제공업체 분석 및 교체에 대한 분석 | [6 empty] | Dana
[2104-S01] Collect Windows Event Log |  | 1. 서버에서 발생하는 이벤트 로그에 대한 수집 2. 저장방식(DB, File) 에 대한 설정
[2104-S02] 전자금융업 중계기관 연동 |  | 1) 전자금융업을 하고 있는 이용사는 코스콤 중계기관과 VPN연동 2) 신규VM장비를 코스콤 중계기관과 연동확인 | [6 empty] | Ravindra | 2021-04-08 | 2021-04-30
[2104-S03] 보유중인 VPN장비에 대한 파악 |  | 1. 보유중인 VPN장비 파악 2. 계정정보 파악 3. 모니터링 확인 방법 파악 | [6 empty] | Ravindra | 2021-04-08 | 2021-04-16
[2104-S04] GME Finance 신용정보취급 자체평가 보고 |  | https://assess.fsec.or.kr/assess/self/assessPrgs.do
[2104-S05] GME Finance IPSEC VPN SETUP |  | GME대부와 코스콤 금융클라우드 IDC간 IPSEC VPN세팅 작업(위드네트웍스)
[2104-S06] Installing a monitoring TV using zabbix |  | 1)Zabbix를 이용한 시스템 모니터링 구성 | [6 empty] | Ravindra | 2021-04-22 | 2021-04-30
[2104-S07] GME-RIA-UAT VPN configuration | [8 empty] | Ravindra
[2105-S01] 대한민국 현장교수 컨설팅
[2105-S02] KISA Security Education
[2105-S03] Setup L3-Switch in Intranet(HQ) |  | 1) L3 스위치를 설치 2) NAC를 L3 로 이동해 설치 3) L2 스위치를 설치 4) VLAN 설정 5) 망연계솔루션을 L3 로 이동해 설치
[2105-S04] Setup VPN in GME대부 |  | 1) 본사에서 Naver클라우드(웨인솔루션)을 접속할 수 있도록 세팅 2) 외부(지점 등)에서 Naver클라우드(웨인솔루션)을 접속할 수 있도록 세팅 | [6 empty] | Ravindra | 2021-05-17 | 2021-05-31
[2101-S05] Setup VM for 정보제공API |  | 1) KFTC 정보제공자 API 2) 코스콤 중계기관 API 3) Active Directory 설정 | [6 empty] | Ravindra | 2021-05-20 | 2021-05-22
[2106-S01] 취약점 점검 |  | 1) 웹/앱 취약점 점검 | [6 empty] | Dana Ravindra | 2021-06-07 | 2021-06-25
Q1 | 안드로이드
Q2 | iOS
Q3 | Core
Q4 | Online
Q5 | Server