## Sheet1
No | Project | Engineer | Development | Unit Test | Total Test | Publish
1 | [2111-02] Change for Access Token Date | Summer, Andrew, Dibya | Nov-19(Fri) | Nov-22(Mon) | Nov-26(Fri) | Nov-30(Tue)
2 | [2111-05] New API for International Topup Country | Subash, Andrew, Dibya | Nov-19(Fri) |  | Nov-26(Fri) | Nov-30(Tue)
3 | [2107-12] 개인정보법-로그인실패횟수제한 | Summer, Andrew, Dibya | Done | Done | Nov-26(Fri) | Nov-30(Tue)
4 | [2107-13] 개인정보법-비밀번호복잡성조건 | Saroj | Done | Done | Nov-26(Fri) | Nov-30(Tue)
5 | [2110-03] Prevent Duplicate Logins | Saroj | Done | Done | Nov-26(Fri) | Nov-30(Tue)
6 | [2109-07] Regualar Change Password | Summer, Andrew, Dibya | Done | Done | Nov-26(Fri) | Nov-30(Tue)
7 | [2110-04] Login using Screen Lock | Summer, Andrew, Nabin | Done | Android Done iOS Testing | Nov-26(Fri) | Nov-30(Tue)
8 | [2109-15] POC using LIAPP-Mobile App Security Solution | Andrew, Nabin | Done | Done | Nov-26(Fri) | Nov-30(Tue)
9 | [2108-09] ATM Deposit using Galaxia | Ram, Andrew, Dibya | Done | Nov-23(Tue) | Nov-26(Fri) | Nov-30(Tue)
10 | [2110-22] Set Default Country is as Native Country in New Recipient | Andrew, Dibya | Andrew개발 체크 |  | Nov-26(Fri) | Nov-30(Tue)
11 | [2110-14] Add Email field from Recipient Registration in African Countries | Ram, Andrew, Dibya | Andrew개발 체크 |  | Nov-26(Fri) | Nov-30(Tue)
12 | [2110-13] Change ATM Withdrawal UI Logic | Andrew, Dibya | Andrew, Dibya 개발체크 |  | Nov-26(Fri) | Nov-30(Tue)
13 | [2109-02] Reward Point Statement in Mobile App (iOS) | Nabin |  |  | Nov-26(Fri) | Nov-30(Tue)
14 | [2108-04] Change Recipient Registration in Overseas Remittance (iOS) | Nabin | Done | Done | Nov-26(Fri) | Nov-30(Tue)
15 | [2108-17] Add Member Terms and Conditions Page after Membership Sign-Up (iOS) | Nabin | Done | Done | Nov-26(Fri) | Nov-30(Tue)
16 | [2107-11] 개인정보법-회원탈퇴기능 (iOS) | Nabin | Done | Done | Nov-26(Fri) | Nov-30(Tue)
17 | [2103-19] OCR function in Mobile App |  |  |  |  | in Dec
18 | [2108-16] Provide for Country default amount on exchange rate page | Subash, Andrew, Dibya | 개발 일정 확인 |  |  | in Dec
19 | [2106-10] Add Real-Name Module in Overseas Remittance | Anil, Preyea, Dibya | Manoj 테스트 시나리오 제작 |  |  | in Dec