## Sheet1
Jul. 15(Mon), 2019
PM : Max,Pralhad |  | Incentive Plan Q 3 ( Jul-Sep)
Phase | Priority | Activity |  | Incentive | Duration | Architent(Design) - Architecture design - DB design - Function list design - Story board(Scenario) | Core | Online | API | iOS,Android | Test(Publish) | Total | Incentive | Incentive(Max Proposal)
Project |  | Project Contents
| 1 | Thunes for Myanmar |  | 100000 | 31st July 2019 | [8 empty] | 300000
| 2 | Lyhour API for Cambodia bank deposit |  | 300000 | 24th July 2019 | [8 empty] | 1500000
| 3 | Inbound (Online, API, App) 2nd phase | Inbound 프로젝트 2번째 페이지 | 500000 | 30th July 2019 | [8 empty] | 2000000
| 4 | Shinhan and IBK bank about accounts created with passport. | 신한은행,IBK 은행은 KFTC만을 이용한 송금 | 200000 | 8th August 2019 | [8 empty] | 700000
| 5 | Agrani bank/Islami Bank not added to new app |  | 100000 | 20th August 2019 | [8 empty] | 300000
| 6 | KJ (Auto-remit for multiple-accounts use) | KJ(복수가상계좌를 이용한 자동송금) | 500000 | 30th August 2019 | [8 empty] | 1500000
| 7 | Mobile app - Registration logic - Calcurator in first screen - Dynamic receiver setup - Send Txn process same as web - Resend method not to check anything | 온라인과 앱에서의 회원가입방식이 달라서 발생하는 문제에 대한 회원가입변경 | 500000 | 29th July 2019 | [8 empty] | 700000
| 8 | Chatting app in app |  | 100000 | 19th July 2019 | [8 empty] | 200000
| 9 | Mobile app popup notice |  | 100000 | 20th August 2019 | [8 empty] | 500000
| 10 | Reward/Coupon System 2nd phase | 포인트/쿠폰 2번째 페이지 | 500000 | 20th August 2019 | [8 empty] | 1000000
| 11 | KFTC(Auto-refund, balance, Domestic-bank transfer) | KFTC(입금이체,잔액조회,로컬은행간 거래) | 1000000 | 15th Sep 2019 | [8 empty] | 1000000
| 12 | Easy Remit | 저축은행 가상계좌 도입 | 500000 | 30th Sep 2019 | [8 empty] | 500000
|  |  |  | 4400000 | [9 empty] | 10200000